## Method Note
Method note: Transport schemes | The South Leicestershire Joint Transport Evidence study (JTE) has not been completed in time to inform this study. To meet the programme for adoption of HBBC’s Local Plan, Phase 3 of the ICS has been prepared ahead of its completion and the Local Plan’s overall transport evidence. An updated Draft South Leicestershire Joint Transport Evidence: Costing Mitigation Report (April 2026) has been published, though, coinciding with this study, that assesses the cost of the mitigation measures identified so far, to inform viability and deliverability assessments. This Mitigation Report has been used to inform the transport infrastructure requirements of the ICS. Whilst the JTE evidence is beneficial to this study, it is not sufficiently evolved to provide more granular detail on the suite of schemes required to enable the Local Plan’s delivery. PLACEHOLDER (FOR HBBC TO VIEW)– Should the follow-up transport modelling study not be delivered prior to ICS publication / LP submission, a statement is required here to explain which sites were excluded from assessment in the draft study above.]

## Housing
Settlement | Site ref | Site address | Housing trajectory to 2045 | Overall site allocation | Scheme Reference ID | Topic | Sub Topic | Project Name | Project Description | Project Notes | Settlement | On-site / Off-site | Delivery body | Other key stakeholder(s) or delivery bodies | Delivery Period | Priority | Cost apportioned to site developer(s) | Estimated cost of total scheme | All funding sources for total scheme | Developer contribution towards expected funding gap | Cost Notes | Deliverability challenges | Overall implementation challenge | Source(s)
[5 empty] | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Anstey | On-site | Developer, Contractor | LCC | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Design Guide.
[5 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Anstey | Off-site | Developer | LCC, National Highways, Warwickshire County Council | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[5 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Anstey | On-site | Developer, Contractor | LCC | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[5 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Anstey | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Anstey | On-site and off-site | Leicestershire Police | HBBC | 2026-2030 | Desirable | 94500 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | Antsey | Off-site | LCC |  | 2026-2030 | Critical | 547150.95 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Antsey | Off-site | LCC |  | 2026-2030 | Critical | 1931121 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that none of the primary schools in Groby can be expanded, therefore around 120 pupils in total can be accomodated but there may be a small shortage of places. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Antsey | Off-site | LCC |  | 2026-2030 | Critical | 1306978.74 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that a 1FE expansion of Brookvale Groby Learning Campus is likely to be required to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Antsey | Off-site | LCC |  | 2026-2030 | Critical | 258265.26 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Antsey | Off-site | LCC |  | 2026-2030 | Critical | 105150.0285 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Antsey | Off-site | LCC |  | 2026-2030 | Critical | 140871.96 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Anstey | Off-site | Cadent Gas | HBBC, Developer | 2026-2030 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Low | Caden Gas analysis submitted to study (March 2026)
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Anstey (Parish) | On-site | Developer |  | 2026-2030 | Essential | £457,949.70 | £457,949.70 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Anstey (Parish) | On-site | HBBC / Local Parish |  | 2026-2030 | Essential | 936414 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Anstey (Parish) | Off-site | HBBC / Local Parish |  | 2026-2030 | Essential | 77015.34 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Anstey (Parish) | Off-site | HBBC / Local Parish |  | 2026-2030 | Essential | 39322.8 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2026-2030 | Critical | 261360 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | NHS ICB did not consider corresponding GP facilities to face any significant deliverabiltiy challenges to expansion. | Low | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
Bagworth | LPR221 | Land West of Station Road, Bagworth | 46 | 46 | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Bagworth (Parish) | On-site | Developer |  | 2026-2030 | Essential | 63000 | 63000 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Bagworth (Parish) | On-site | HBBC / Local Parish |  | 2026-2030 | Essential | 24500 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Bagworth (Parish) | Off-site | HBBC / Local Parish |  | 2026-2030 | Essential | 462000 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Bagworth (Parish) | Off-site | HBBC / Local Parish |  | 2026-2030 | Essential | 185500 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Bagworth | On-site and off-site | Leicestershire Police | HBBC | 2026-2030 | Desirable | 16100 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2026-2030 | Essential | 26459 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2026-2030 | Essential | 20460 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2026-2030 | Essential | 3581 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2026-2030 | Essential | 1655 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2026-2030 | Essential | 990 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Bagworth | Off-site | LCC |  | 2026-2030 | Critical | 329005.8 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Bagworth | Off-site | LCC |  | 2026-2030 | Critical | 222670.452 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated a 0.5-1FE expansion of South Charnwood High School may be required to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Bagworth | Off-site | LCC |  | 2026-2030 | Critical | 4840.0823 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Bagworth | Off-site | Cadent Gas | HBBC, Developer | 2026-2030 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Low | Caden Gas analysis submitted to study (March 2026)
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2026-2030 | Critical | 44528 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | One of two nearby surgeries identified as not having space for expansion. The other applicable surgery can expand but would require travel from the proposed site. | Medium | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
Barlestone | AS455 | Land North of Barton Road, Barlestone | 128 | 128 | TR03 | Transport | Active Travel | Off-Site Footway Construction | Construction of a footway along Barton Road with associated crossing infrastructure | To be delivered prior to occupation as part of access proposals | Barlestone | Off-site | Developer, Contractor | LCC | 2031-2035 | Critical | 70000 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Low | Planning Application - Publicly available
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Barlestone | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 44800 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution towards other sources of funding for wider scheme | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | Barlestone | Off-site | LCC |  | 2031-2035 | Critical | 259390.08 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Barlestone | Off-site | LCC |  | 2031-2035 | Critical | 915494.4 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that the nearest primary school to this development is Barlestone C of E Primary School.This is currently forecast to be full by 2030 and it may not be possible to extend this school due to site constraints. However, it is noted that pupil numbers may be accomodated across a variety of school sites. For example, a 1.5FE expansion at St Peters in Market Bosworth may provide a solution. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Barlestone | Off-site | LCC |  | 2031-2035 | Critical | 619604.736 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Barlestone | Off-site | LCC |  | 2031-2035 | Critical | 122436.864 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Barlestone | Off-site | LCC |  | 2031-2035 | Critical | 49848.9024 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Barlestone | Off-site | LCC |  | 2031-2035 | Critical | 66778.624 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 123904 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | Existing applicable surgeries have limited spare capacity. Proposed development across Market Bosworth and Desford would pose challenges for meeting new demand. | Medium | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Barlestone | Off-site | Cadent Gas | HBBC, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Low | Caden Gas analysis submitted to study (March 2026)
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Barlestone (Parish) | On-site | Developer |  | 2031-2035 | Essential | 217102.08 | 217102.08 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Barlestone (Parish) | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 443929.6 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Barlestone (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 36510.98 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Barlestone (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 18641.92 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
Barwell | AS58 | Barwell Sustainable Urban Extension (SUE) | 1961 | 2500 | TR04 | Transport | Bus | Enhancement of number 2 bus service | The enhanced 2 service will compliment the existing service between Barwell and Hinckley, and provide further connections to Hinckley rail station which will make use of the proposed improvements to the rail station and creation of a public transport interchange. | The enhancement of this service will align with the phasing of the development, with a 30 minute frequency service (one additional bus) being provided at occupation of 1,250 dwellings, and the 20 minute frequency service being provided at full occupation. | Barwell | Off-site | Developer, Bus Operator | LCC | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR05 | Transport | Bus | Bus Stop Construction | Bus stops to be constructed along Stapleton Lane which is along the 159 Route | Exact locations to be confirmed upon engagement with stakeholders | Barwell | Off-site | LCC | Bus operator | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR06 | Transport | Bus | Bus Stop Construction | Bus stops to be constructed internally within the site within 400m walking distance of occupiers, with shelters, raised kerbing, bus service information | Subject to masterplan design principles | Barwell | On-site | LCC | Bus operator, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR07 | Transport | Bus | Bus service information | A financial contribution can be made to the provision of public transport infrastructure and the implementation of Real Time Passenger Information (RTPI). | Funding will be provided for a set period following full occupation in order to assist the service in reaching commerciality. | Barwell | Off-site | LCC | Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR08 | Transport | Active Travel | Internal Walking and Cycling routes | Within the site, a series of shared footway / cycle tracks will be provided along with retention/diversion of existing walk routes, as indicated below. The principles of these include: - Partial diversion of the public footpath no. U36 forming part of the Leicestershire Round to within a landscaped area; - A new footpath/ cycle path along the western edge of the site connecting PROW T99 and T58; - Retention and/or minor diversions of the following PROWs, U33, U35, T58, T97 and T99; - A new footpath/ cycle path from PROW U36, the Leicestershire Round, to Hinckley Road to the south west of the site; and - Retention and partial diversion of existing public footpaths within the site, which link to Mill Street, Moat Way, and Hereford Close / Galloway Close | To be designated within site masterplan | Barwell | On-site | Developer, Contractor |  | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR09 | Transport | Active Travel | Connection to Public right of way | There is also potential to upgrade the existing PROWs in Barwell to provide enhanced pedestrian and cycle connectivity for existing and future residents of Barwell and Barwell SUE. | No exact scheme proposed at this stage | Barwell | Off-site | LCC | Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR10 | Transport | Active Travel | Production of Framework Travel Plan | Applicant to appoint a travel plan coordinator to enforce the proposals within the Framework Travel Plan | The Framework Travel Plan would remain a ‘living document’, that will evolve and be updated by the Framework Travel Plan Coordinator to respond to local traffic conditions and opportunities for sustainable transport promotion, including schemes being implemented by the local highway authority and local transport stakeholders including bus operators. | Barwell | Off-site | Developer |  | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | S106 contribution from AS58 Barwell SUE to be used towards: - A5 Longshoot / Dodwells - Desford Crossroads junction improvement - Public Right of Way Improvements as detailed within the submitted documents - Ashby Road / Normandy Way junction improvement - Travel Packs - Travel Plan Monitoring Fee | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | S106 agreement for 12/00295/OUT
[5 empty] | TR11 | Transport | Highways | Off-site Junction Improvements | A47 Normandy Way/A447 Ashby Road - Provision of a 100m widened southbound approach to include two approach lanes; Provision of a two-lane westbound exit from the junction; provision of a three lane northbound approach including a signal-controlled dedicated left turn lane; provision of a two lane exit to Normandy Way west and signal-controlled cycle and pedestrian crossing facilities | Proportionate financial contribution to LCC through s106 to design, consult on and implement a scheme of improvements that provides adequate mitigation of growth at Barwell and Earl Shilton | Barwell | Off-site | LCC | Developer | 2031-2035 | Critical | 12407711 | Cost subject to ongoing scoping and development | S106, Local Authority / Central Government Funding | Developer contibution pooled with contributions from multiple sites. Pooled contributiions may need to contribute to other potential funding sources to deliver scheme | S106 contribution from AS58 Barwell SUE to be used towards: - A5 Longshoot / Dodwells - Desford Crossroads junction improvement - Public Right of Way Improvements as detailed within the submitted documents - Ashby Road / Normandy Way junction improvement - Travel Packs - Travel Plan Monitoring Fee | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Medium | S106 agreement for 12/00295/OUT
[5 empty] | TR15 | Transport | Highways | Off-site Junction Improvements | A5/Dodwells Junction Improvement Scheme - Additional Lane on Dodwells Road | Contribution defined within agreed S106 | Barwell | Off-site | LCC | Developer | 2031-2035 | Critical | Information not yet available | 1901750 | S106, Local Authority, Central Government Funding | Developer contibution pooled with contributions from multiple sites. Pooled contributiions may need to contribute to other potential funding sources to deliver scheme | S106 contribution from AS58 Barwell SUE to be used towards: - A5 Longshoot / Dodwells - Desford Crossroads junction improvement - Public Right of Way Improvements as detailed within the submitted documents - Ashby Road / Normandy Way junction improvement - Travel Packs - Travel Plan Monitoring Fee | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Medium | JTE Study April 2026
[5 empty] | WA1 | Waste |  | Waste services contributions | Contribution towards waste facilities resulting from increased demand for services from site development (unspecified) | Unspecified amount outlined within cabinet report | Barwell | Off-site | HBBC and LCC |  | 2031-2035 | Critical | Information not yet available | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, central government, EPR scheme | Developer contribution towards other sources of funding for wider scheme | No cost details are provided in the relevant planning agreement document. | None currently identified | Unclear | Cabinet Meeting (7 February 2020) to update the Cabinet on the completion of the S106 agreement for 12/00295/OUT
| LPR185 | Land South of New Barn Farm, Kirkby Road, Barwell | 60 | 60 | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 58080 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | NHS ICB did not consider corresponding GP facilities to face any significant deliverabiltiy challenges to expansion. | Low | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | TR12 | Transport | Active Travel | Off-Site Footway Construction | New footway construction along Kirkby Road to connect to existing pedestrian infrastructure | Outline Design Stage | Barwell | Off-site | LCC | Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | Substantive response provided by LCC Highways on 12 September 2025 requesting further details. | Low | Planning Application - Publicly available
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 34324 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 26543 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 4646 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Barwell vicinity (likely Hinckley Town Tennis Club or Desford Lane Tennis Club) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 2147 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Barwell (Barwell Bowls Club) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 1285 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Desford | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 21000 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | EL1 | Electric | Network upgrades | Off site reinforcement - Electricity | Upgrades to electricity network to service proposed development site | National Grid Electricity Distribution grid capacity assessment indicates that work will be required to service the proposed development site given current capacity constraints in the vicinity. | Desford | Off-site | National Grid Electricity Distribution |  | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | NGED | None | Developer not expected to pay for off-site reinforcement. Utility provider solely responsible for funding. | None currently identified | Unclear | Arup assessment against National Grid Electricity Distribution online Capacity Maps submitted for Phase 2 Addendum study - Autumn 2025
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Barwell (Parish) | On-site | Developer |  | 2031-2035 | Essential | 101766.6 | 101766.6 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Barwell (Parish) | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 208092 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Barwell (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 17114.52 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Barwell (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 8738.4 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
Desford | LPR151 A | Land South of Desford, Desford | 550 | 550 | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Desford | On-site | Developer, Contractor | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Design Guide.
[5 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Desford | Off-site | Developer | LCC, National Highways, Warwickshire County Council | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[5 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Desford | On-site | Developer, Contractor | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[5 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Desford | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | Desford | Off-site | LCC |  | 2031-2035 | Critical | 1114566.75 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Desford | Off-site | LCC |  | 2031-2035 | Critical | 3933765 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that Desford Primary School may be expanded by 1FE to make it a 3FE school to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Desford | Off-site | LCC |  | 2031-2035 | Critical | 2662364 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated Bosworth Academy may be expanded by 2FE to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Desford | Off-site | LCC |  | 2031-2035 | Critical | 526095.9 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated Bosworth Academy (post 16 provision) may be expanded by approximately 100 places to accommodate pupils from this development, if needed. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Desford | Off-site | LCC |  | 2031-2035 | Critical | 214194.5025 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Desford | Off-site | LCC |  | 2031-2035 | Critical | 286961.4 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Desford-vicinity (likely Bosworth Academy Pool) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 314643 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Desford-vicinity (likely Sport in Desford) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 243312 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 42586 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Desford-vicinity (likely Desford Lawn Tennis Club at Sport in Desford ) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 19683 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Desford-vicinity (likely Desford Bowls Club at Sport in Desford) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 11777 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S06 | Sports | Pitches | Pitches | Pitch provision (natural grass pitches only) - capital cost | In line with Sports England requirements, provision of pitches (total pitch capital cost) | Desford-vicinity (likely Kirkby Road and Pecleton Lane Pitches) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 151998 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S07 | Sports | Pitches | Pitch maintenance | Lifecycle cost for pitch maintenance per annum (applied across 10-year period) (natural grass pitches only) | In line with Sports England requirements, provision of costs for maintenance lifecycle (cost per annum of pitches) | Desford-vicinity (likely Kirkby Road and Pecleton Lane Pitches) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 29826 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Grass Pitch Maintenance Fund, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S08 | Sports | Pitches | Changing rooms | Provision of changing rooms for provided pitches (natural grass pitches only) | In line with Sports England requirements, provision of cost for changing rooms (total capital cost) | Desford-vicinity (likely Kirkby Road and Pecleton Lane Pitches) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 302378 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Desford | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 192500 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | G02 | Gas | Network upgrades | Off site reinforcement - Medium Pressure Gas | Upgrades to medium pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Desford | Off-site | Cadent Gas | HBBC, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
[5 empty] | WW01 | Wastewater | Network upgrades | Off site capacity upgrades - Sewerage | Upgrades to sewage treatment work and/or receiving sewerage network to service proposed development site | STW’s desktop review identified that the site’s known network constraints are that the size of site will likely have an adverse impact on the downstream network and PS performance.and that it is assumed to be able to connect to the PS Desford - Bambrook Close northwest of the site. The northeast section of the site will require pumping due to topography, while the southwest section can be gravity connected. | Desford | Off-site | Severn Trent Water | HBBC | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | Severn Trent Water | None | All network upgrade works required due to growth are funded through Severn Trent Water's Asset Management Programme (AMP) cycle. Developers are unlikely to be asked for a contribution. | None currently identified | Unclear | Severn Trent Water assessment of sewerage provision for proposed development sites submitted as part of this study
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Desford (Parish) | On-site | Developer |  | 2031-2035 | Essential | 932860.5 | 932860.5 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Desford (Parish) | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 1933382 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Desford (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 122648.9 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Desford (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 67166 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
| LPR86 | Land off Barns Way and North of Leicester Lane, Desford | 70 | 70 | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 67760 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | One of two applicable surgeries identified as not having space for expansion and would require relocation. | Medium | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Desford-vicinity (likely Bosworth Academy Pool) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 40045 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 30967 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 5420 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Desford-vicinity (likely Desford Lawn Tennis Club at Sport in Desford) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 2505 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Desford-vicinity (likely Desford Bowls Club at Sport in Desford) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 1499 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Desford | Off-site | LCC |  | 2031-2035 | Critical | 500661 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that Desford Primary School may be expanded by 1FE to make it a 3FE school to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Desford | Off-site | LCC |  | 2031-2035 | Critical | 338846.34 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated Bosworth Academy may be expanded by 2FE to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Desford | Off-site | LCC |  | 2031-2035 | Critical | 66957.66 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated Bosworth Academy (post 16 provision) may be expanded by approximately 100 places to accommodate pupils from this development, if needed. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Desford (Parish) | On-site | Developer |  | 2031-2035 | Essential | 118727.7 | 118727.7 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Desford (Parish) | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 242774 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Desford (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 19966.94 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Desford (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 10194.8 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
Earl Shilton | AS237 | Earl Shilton Sustainable Urban Extension (SUE) | 1581 | 1581 | TR13 | Transport | Bus | Enhancement of number 1 bus service | The enhanced 1 service will offer an increased frequency | This is a temporary measure until internal spine road completed upon which a new bus service will run through site | East Shilton | Off-site | LCC | Developer, Bus operator | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | Overall scheme implementation cost not known | None currently identified. Substantive response provided by LCC Highways on 17 May 2024 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR14 | Transport | Active Travel | Internal Walking and Cycling routes | An extensive network of shared use walking and cycling routes within the site which also connect to the existing external network, including Astley Road, Masefield Road, Mill Lane, Breach Lane and Avenue South; complemented by wayfinding | Tie into existing | East Shilton | On-site | Developer |  | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 17 May 2024 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR16 | Transport | Active Travel | Off Site Pedestrian/cyclist improvement | Construction of a footway/cycleway on the A47 between the Leicester Road/Clickers Way roundabout and the junction of Desford Crossroads | n/a | East Shilton | Off-site | LCC | Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106, Local Authority Funding, Consolidated Active Travel Fund | Developer contribution towards other sources of funding for wider scheme | Scheme has not been submitted to planning yet | None currently identified. Substantive response provided by LCC Highways on 17 May 2024 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR22 | Transport | Highways | Off-site Junction Improvements | Desford Lane Junction Improvement Scheme - Junction to be upgraded to a signalised junction | Contribution agreed through S106 | East Shilton | Off-site | LCC | Developer | 2031-2035 | Critical | 3548891 | 12408711 | S106, Local Authority Funding | Developer contibution pooled with contributions from multiple sites. Pooled contributiions may need to contribute to other potential funding sources to deliver scheme | East Shilton SUE is liable for 28.6% of growth within junction hence how this has been calculated | None currently identified. Substantive response provided by LCC Highways on 17 May 2024 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Earl Shilton | Off-site | Cadent Gas | HBBC, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
[5 empty] | WW01 | Wastewater | Network upgrades | Off site capacity upgrades - Sewerage | Upgrades to sewage treatment work and/or receiving sewerage network to service proposed development site | STW’s desktop review identified that the site’s known network constraints are predicted flooding upstream of combined sewer. Size of site will likely have an adverse impact on the sewerage network. and that it is assumed to be able to connect to 375mm combined sewer flowing to STW. Parts of site will require pumping due to topography | Earl Shilton | Off-site | Severn Trent Water | HBBC | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | Severn Trent Water | None | All network upgrade works required due to growth are funded through Severn Trent Water's Asset Management Programme (AMP) cycle. Developers are unlikely to be asked for a contribution. | None currently identified | Unclear | Severn Trent Water assessment of sewerage provision for proposed development sites submitted as part of this study
[5 empty] | EL1 | Electric | Network upgrades | Off site reinforcement - Electricity | Upgrades to electricity network to service proposed development site | National Grid Electricity Distribution grid capacity assessment indicates that work will be required to service the proposed development site given current capacity constraints in the vicinity. | Earl Shilton | Off-site | National Grid Electricity Distribution |  | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | NGED | None | Developer not expected to pay for off-site reinforcement. Utility provider solely responsible for funding. | None currently identified | Unclear | Arup assessment against National Grid Electricity Distribution online Capacity Maps submitted for Phase 2 Addendum study - Autumn 2025
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement or extension to Health Lane Surgery; or Barwell & Holly Croft Medical Centres; and or any other Healthcare infrastructure designed to support local patients’ healthcare needs. | Enhancement or extension to specified GP practices or other healthcare infrastructure capacity development specified in associated planning agreement. Details of affected GP surgeries extracted from latest planning agreement with HBBC | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 1161600 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Cost to site developer extracted from latest planning agreement with HBBC | Two of four applicable surgeries identified as not having space for expansion. | Medium | Planning agreement & Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB (for Deliverability Challenges only)
| LPR200 + LPR216 | Land South East of the A47, Earl Shilton | 1932 | 2513 | TR38 | Transport | Active Travel | Cycling Infrastructure | Cycling Route I | Contained within JTE evidence. Further details to be provided in LCWIP. | Earl Shilton | Off-site | LCC | Developer | 2031-2035 | Essential | 2742336 | 2742336 | S106, Local Authority Funding | Fully funded by developer | To be funded by LPR200 according to JTE Costing Mitigation Report | LCWIP hasn't been published. Priority of route unknown. | Low | JTE Study April 2026
[5 empty] | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Earl Shilton | On-site | Developer, Contractor | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Design Guide.
[5 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Earl Shilton | Off-site | Developer | LCC, National Highways, Warwickshire County Council | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[5 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Earl Shilton | On-site | Developer, Contractor | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[5 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Earl Shilton | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | On-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 1105302 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | On-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 854726 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | On-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 149600 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | On-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 69143 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Earl Shilton (likely Kingscroft Bowls Club) | On-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 41371 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S06 | Sports | Pitches | Pitches | Pitch provision (natural grass pitches only) - capital cost | In line with Sports England requirements, provision of pitches (total pitch capital cost) | Earl Shilton (likely Weaver Springs Sports Park) | On-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 533993 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S07 | Sports | Pitches | Pitch maintenance | Lifecycle cost for pitch maintenance per annum (applied across 20-year period) (natural grass pitches only) | In line with Sports England requirements, provision of costs for maintenance lifecycle (cost per annum of pitches) | Earl Shilton (likely Weaver Springs Sports Park) | On-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 104783 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Grass Pitch Maintenance Fund, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S08 | Sports | Pitches | Changing rooms | Provision of changing rooms for provided pitches (natural grass pitches only) | In line with Sports England requirements, provision of cost for changing rooms (total capital cost) | Earl Shilton (likely Weaver Springs Sports Park) | On-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 1062267 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | P02 | Policing |  | Policing and Community Safety Contributions | Fluid infrastructure approach to policing and community safety capacity needs proposed by Leicestershire Police with additional identified requirement for additional on-site mitigation (for example, early phase PCSOs and more intensive community safety measures). | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives as well as Community Support Officers. | Earl Shilton | On-site and off-site | Leicestershire Police | HBBC | 2026 - 2045 | Desirable | 1005200 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | Earl Shilton | Off-site | LCC |  | 2031-2035 | Critical | 5092556.805 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Earl Shilton | Off-site | LCC |  | 2031-2035 | Critical | 17973729.9 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that 4FE (ideally two 2FE schools) are likely to be required to accommodate pupils from this development. These could be built as 1FE+ schools to help phase these works. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Earl Shilton | On-site | LCC |  | 2031-2035 | Critical | 12164583.606 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that a 6FE secondary school is likely to be required to accommodate pupils from this development, ideally on-site at LPR200 + LPR216. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Earl Shilton | Off-site | LCC |  | 2031-2035 | Critical | 2403779.994 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated Bosworth Academy (post 16 provision) may be expanded by approximately 100 places to accommodate Additionally, the post 16 provision to be included at Stoney Stanton may also accomodate the pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Earl Shilton | Off-site | LCC |  | 2031-2035 | Critical | 978674.1541 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Earl Shilton | Off-site | LCC |  | 2031-2035 | Critical | 1311152.724 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 2432584 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | Two of four applicable surgeries identified as not having space for expansion. | Medium | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Earl Shilton | Off-site | Cadent Gas | HBBC, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
[5 empty] | WW01 | Wastewater | Network upgrades | Off site capacity upgrades - Sewerage | Upgrades to sewage treatment work and/or receiving sewerage network to service proposed development site | STW’s desktop review identified that the site’s known network constraints are that a site of this size would likely cause some adverse impact on nearby combined system, which may necessitate the requirement to connect flows derived from this development to the works inlet, or into the network just upstream of the works and as the site is located nearby to the sewage treatment works, it could connect directly into the inlet or into the network just upstream of the works. | Earl Shilton | Off-site | Severn Trent Water | HBBC | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | Severn Trent Water | None | All network upgrade works required due to growth are funded through Severn Trent Water's Asset Management Programme (AMP) cycle. Developers are unlikely to be asked for a contribution. | None currently identified | Unclear | Severn Trent Water assessment of sewerage provision for proposed development sites submitted as part of this study
[5 empty] | EL1 | Electric | Network upgrades | Off site reinforcement - Electricity | Upgrades to electricity network to service proposed development site | National Grid Electricity Distribution grid capacity assessment indicates that work will be required to service the proposed development site given current capacity constraints in the vicinity. | Earl Shilton | Off-site | National Grid Electricity Distribution |  | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | NGED | None | Developer not expected to pay for off-site reinforcement. Utility provider solely responsible for funding. | None currently identified | Unclear | Arup assessment against National Grid Electricity Distribution online Capacity Maps submitted for Phase 2 Addendum study - Autumn 2025
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Earl Shilton (Parish) | On-site | Developer |  | 2031-2035 | Essential | 4262324.43 | 4262324.43 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Earl Shilton (Parish) | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 9447573.24 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
Groby | LPR146 A + LPR146 B | Land South of Sacheverell Way, Groby | 180 | 180 | TR23 | Transport | Highways | Off-site Junction Improvements | Groby Road/Sacheverell Way Junction Improvement Scheme - Junction to be upgraded to a signalised junction | Contribution still to be agreed through S106 | Groby | Off-site | LCC | Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106, Local Authority Funding | Developer contribution towards other sources of funding for wider scheme |  | Substantive response provided by LCC Highways on 26 March 2026 requesting further details. | Medium | Planning Application - Publicly available
[5 empty] | TR29 | Transport | Bus | Bus Service/Infrastructure | Routing of 27 service to run closer to or within the site, requiring new bus stop infrastructure | No proposal at this stage | Groby | On-site and off-site | Developer | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | Requirement for site to access sufficient bus service | Substantive response provided by LCC Highways on 26 March 2026 requesting further details. | Low | Planning Application - Publicly available
[5 empty] | TR30 | Transport | Active Travel | Off-Site Walking Infrastructure | Proposed pedestrian refuge on Sacherevell Way to aid crossing movements | Two proposed crossings - one on the desire line from Brookvale College and to the east of the site | Groby | Off-site | Developer | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | Requirement for site to be accessed safely | Substantive response provided by LCC Highways on 26 March 2026 requesting further details. | Low | Planning Application - Publicly available
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 102974 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 79629 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Groby (likely Groby/Brookvale Campus) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 13937 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Groby (likely Groby/Brookvale Campus) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 6442 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 3854 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | Groby | Off-site | LCC |  | 2031-2035 | Critical | 364767.3 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Groby | Off-site | LCC |  | 2031-2035 | Critical | 1287414 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that none of the primary schools in Groby can be expanded, therefore around 120 pupils in total can be accomodated but there may be a small shortage of places. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Groby | Off-site | LCC |  | 2031-2035 | Critical | 871319.16 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that a 1FE expansion of Brookvale Groby Learning Campus is likely to be required to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Groby | Off-site | LCC |  | 2031-2035 | Critical | 172176.84 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Groby | Off-site | LCC |  | 2031-2035 | Critical | 70100.019 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Groby | Off-site | LCC |  | 2031-2035 | Critical | 93914.64 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 174240 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | NHS ICB did not consider corresponding GP facilities to face any significant deliverabiltiy challenges to expansion. | Low | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Groby | Off-site | Cadent Gas | HBBC, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Groby | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 63000 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
Higham on the Hill | LPR181 | Land Between the A5 and Northwood Farm, Wood Lane, Higham on the Hill | 70 | 70 | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Higham on the Hill | On-site | Developer, Contractor | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Design Guide.
[5 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Higham on the Hill | Off-site | Developer | LCC, National Highways, Warwickshire County Council | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[5 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Higham on the Hill | On-site | Developer, Contractor | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[5 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Higham on the Hill | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 26459 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 20460 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 3581 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Higham on the Hill (likely Hollycroft Park) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 1655 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Higham on the Hill (likely Hollycroft Park) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 990 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Higham on the Hill | Off-site | LCC |  | 2031-2035 | Critical | 500661 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that there is unlikely to be capacity in Higham on the Hill C of E Primary School, with no other primary schools in a 2 mile radius. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Higham on the Hill | Off-site | LCC |  | 2031-2035 | Critical | 338846.34 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Higham on the Hill | Off-site | LCC |  | 2031-2035 | Critical | 66957.66 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that The Hinckley School may be expanded by around 100 places to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 67760 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | NHS ICB did not consider corresponding GP facilities to face any significant deliverabiltiy challenges to expansion. | Low | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Higham on the Hill | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 24500 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Higham on the Hill (Parish) | On-site | Developer |  | 2031-2035 | Essential | 118727.7 | 118727.7 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Higham on the Hill (Parish) | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 242774 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Higham on the Hill (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 19966.94 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Higham on the Hill (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 10194.8 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
Hinckley | AS1029, AS1031 A, AS1031 B and LPR199 | Land North of Normandy Way, 'Hinckley North', Hinckley | 1320 | 1320 | TR15 | Transport | Highways/Bus | Off-site Junction Improvements | A5/Dodwells Junction Improvement Scheme - Additional Lane on Dodwells Road | Contribution defined within agreed S106 | Hinckley | Off-site | LCC | Developer | 2031-2035 | Critical | 1043552.24 | 1901750 | S106, Local Authority / Central Government Funding | Developer contibution pooled with contributions from multiple sites. Pooled contributiions may need to contribute to other potential funding sources to deliver scheme | Information on the costing is derived from the 2026 JTE study and will be funded through a mix of S106 contributions from other sites | Highways contribution agreed in conjunction with planning consent 24/00264/OUT. Contribution in the S106 Agreement is different to the JTE evidence. | Medium | JTE Study April 2026
[5 empty] | TR11 | Transport | Highways | Off-site Junction Improvements | A47 Normandy Way/A447 Ashby Road - Provision of a 100m widened southbound approach to include two approach lanes; Provision of a two-lane westbound exit from the junction; provision of a three lane northbound approach including a signal-controlled dedicated left turn lane; provision of a two lane exit to Normandy Way west and signal-controlled cycle and pedestrian crossing facilities | Proportionate financial contribution to LCC through s106 to design, consult on and implement a scheme of improvements that provides adequate mitigation of growth at Barwell and Earl Shilton | Hinckley | Off-site | LCC | Developer | 2031-2035 | Critical | 471789.47 | Cost subject to ongoing scoping and development | S106, Local Authority / Central Government Funding | Developer contibution pooled with contributions from multiple sites. Pooled contributiions may need to contribute to other potential funding sources to deliver scheme | Funded through a mix of S106 contributions from other sites | Highways contribution agreed in conjunction with planning consent 24/00264/OUT. Total funding package for schem needs to be identified. | Medium | Planning Application - Publicly available
[5 empty] | TR17 | Transport | Active Travel | Off-Site Footway Construction | New Footway Construction along Stoke Road to connect to existing Bus stop infrastructure and walking/cycling infrastructure. Also relevant Toucan crossing infrastructure along the A47 | Outline Design Stage | Hinckley | Off-site | Developer | LCC | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S278 | Developer contribution towards other sources of funding for wider scheme | Funded through a mix of S106 contributions from other sites | Highways contribution agreed in conjunction with planning consent 24/00264/OUT. Total funding package for schem needs to be identified. | Medium | Planning Application - Publicly available
[5 empty] | TR39 | Transport | Active Travel | Cycling Infrastructure | Cycling Route L | Contained within JTE evidence. Further details to be provided in LCWIP. | Hinckley | Off-site | LCC | Developer | 2031-2035 | Essential | 928512 | 928512 | S106, Local Authority Funding | Fully funded by developer | Funded through S106 | LCWIP hasn't been published. Priority of route unknown. | Low | JTE Study April 2026
[5 empty] | TR40 | Transport | Active Travel | Cycling Infrastructure | Cycling Route M | Contained within JTE evidence. Further details to be provided in LCWIP. | Hinckley | Off-site | LCC | Developer | 2031-2035 | Essential | 10053151 | 10863889 | S106, Local Authority Funding | Developer contribution towards other sources of funding for wider scheme | Funded through a mix of local authority and S106 contributions | LCWIP hasn't been published. Priority of route unknown. | Low | JTE Study April 2026
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 755143 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 583949 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Hinckley (likely St Martins School/ or venue supported by Football Foundation) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 102207 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Hinckley (likely Hinckley Town Tennis Club) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 47238 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Hinckley (likely Hollycroft Park) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 28264 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S06 | Sports | Pitches | Pitches | Pitch provision (natural grass pitches only) - capital cost | In line with Sports England requirements, provision of pitches (total pitch capital cost) | Hinckley (likely Clarendon Park or Richmond Park) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 364822 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S07 | Sports | Pitches | Pitch maintenance | Lifecycle cost for pitch maintenance per annum (applied across 10-year period) (natural grass pitches only) | In line with Sports England requirements, provision of costs for maintenance lifecycle (cost per annum of pitches) | Hinckley (likely Clarendon Park or Richmond Park) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 71587 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Grass Pitch Maintenance Fund, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S08 | Sports | Pitches | Changing rooms | Provision of changing rooms for provided pitches (natural grass pitches only) | In line with Sports England requirements, provision of cost for changing rooms (total capital cost) | Hinckley (likely Clarendon Park) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 725732 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | E01 | Education | Early Years | Early Years Contribution | Contributions to Early Years expansions | Early years contribution agreed upon in planning agreements for the site. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | £647.507.90 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106 | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 9441036 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that 1FE primary school expansion (location TBD) and a new 2FE+ school may be required to accommodate pupils from this development. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 6389673.84 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that a new 6FE secondary school may be required to accommodate pupils from this development. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 1262630.16 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that if a new secondary school is built, this should contain post 16 provision to accommodate pupils from this development. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 514066.806 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 688707.36 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 1277760 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | NHS ICB indicated that local GP practices may struggle to accommodate the cumulative amount of growth planned across Hinckley, given existing challenges to expansion at those practices. | Medium | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | P02 | Policing |  | Policing and Community Safety Contributions | Fluid infrastructure approach to policing and community safety capacity needs proposed by Leicestershire Police with additional identified requirement for additional on-site mitigation (for example, early phase PCSOs and more intensive community safety measures). | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives as well as Community Support Officers. | New Settlement | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 462000 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Hinckley | Off-site | Cadent Gas | HBBC, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
[5 empty] | WW01 | Wastewater | Network upgrades | Off site capacity upgrades - Sewerage | Upgrades to sewage treatment work and/or receiving sewerage network to service proposed development site | STW’s desktop review identified that the site’s known network constraints are a site of this size would likely cause an adverse impact on the nearby sewerage infrastructure and probably necessitate a capital scheme to mitigate network capacity risk and depending on the outputs of the hydraulic modelling sewer capacity assessment, a development of this site could connect into the network at several locations depending on where has suitable capacity. | Hinckley | Off-site | Severn Trent Water | HBBC | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | Severn Trent Water | None | All network upgrade works required due to growth are funded through Severn Trent Water's Asset Management Programme (AMP) cycle. Developers are unlikely to be asked for a contribution. | None currently identified | Unclear | Severn Trent Water assessment of sewerage provision for proposed development sites submitted as part of this study
[5 empty] | EL1 | Electric | Network upgrades | Off site reinforcement - Electricity | Upgrades to electricity network to service proposed development site | National Grid Electricity Distribution grid capacity assessment indicates that work will be required to service the proposed development site given current capacity constraints in the vicinity. | Hinckley | Off-site | National Grid Electricity Distribution |  | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | NGED | None | Developer not expected to pay for off-site reinforcement. Utility provider solely responsible for funding. | None currently identified | Unclear | Arup assessment against National Grid Electricity Distribution online Capacity Maps submitted for Phase 2 Addendum study - Autumn 2025
[5 empty] | WA1 | Waste |  | Waste services contributions | Contribution towards waste facilities resulting from increased demand for services from site development (unspecified) | £49.53 per dwelling up to a maximum of £20,554.95 | Hinckley | Off-site | HBBC and LCC |  | 2031-2035 | Critical | 20554.95 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, central government, EPR scheme | Developer contribution towards other sources of funding for wider scheme | Planning agreement identifies factor cost contribution towards waste of £49.53 per dwelling up to a maximum of £20,554.95 | None currently identified | Unclear | S106 agreement for 24/00264/OUT
| LPR31 | Land West of Hollycroft Grange, Hinckley | 530 | 530 | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Hinckley | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 185500 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Hinckley | On-site | Developer, Contractor | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Design Guide.
[5 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Hinckley | Off-site | Developer | LCC, National Highways, Warwickshire County Council | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[5 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Hinckley | On-site | Developer, Contractor | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[5 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Hinckley | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 303201 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 234464 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 41038 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Hinckley (likely Hinckley Town Tennis Club) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 18967 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 11349 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S06 | Sports | Pitches | Pitches | Pitch provision (natural grass pitches only) - capital cost | In line with Sports England requirements, provision of pitches (total pitch capital cost) | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 146469 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S07 | Sports | Pitches | Pitch maintenance | Lifecycle cost for pitch maintenance per annum (applied across 10-year period) (natural grass pitches only) | In line with Sports England requirements, provision of costs for maintenance lifecycle (cost per annum of pitches) | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 28741 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Grass Pitch Maintenance Fund, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S08 | Sports | Pitches | Changing rooms | Provision of changing rooms for provided pitches (natural grass pitches only) | In line with Sports England requirements, provision of cost for changing rooms (total capital cost) | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 291356 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 3790719 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that 1FE primary school expansion (location TBD) and a new 2FE+ school may be required to accommodate pupils from this development. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 2565550.86 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that a new 6FE secondary school may be required to accommodate pupils from this development. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 506965.14 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that if a new secondary school is built, this should contain post 16 provision to accommodate pupils from this development. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 206405.6115 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 276526.44 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 513040 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | NHS ICB indicated that local GP practices may struggle to accommodate the cumulative amount of growth planned across Hinckley, given existing challenges to expansion at those practices. | Medium | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Hinckley | Off-site | Cadent Gas | HBBC, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
[5 empty] | WW01 | Wastewater | Network upgrades | Off site capacity upgrades - Sewerage | Upgrades to sewage treatment work and/or receiving sewerage network to service proposed development site | STW’s desktop review identified that the site’s known network constraints are that there is some model predicted flooding downstream of the likely connection point. It is likely a development of this size will adversely impact the sewerage infrastructure. and that it is assumed to be able to connect to the local wastewater network by development could join 150mm foul sewer to the east of the site. | Hinckley | Off-site | Severn Trent Water | HBBC | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | Severn Trent Water | None | All network upgrade works required due to growth are funded through Severn Trent Water's Asset Management Programme (AMP) cycle. Developers are unlikely to be asked for a contribution. | None currently identified | Unclear | Severn Trent Water assessment of sewerage provision for proposed development sites submitted as part of this study
[5 empty] | EL1 | Electric | Network upgrades | Off site reinforcement - Electricity | Upgrades to electricity network to service proposed development site | National Grid Electricity Distribution grid capacity assessment indicates that work will be required to service the proposed development site given current capacity constraints in the vicinity. | Hinckley | Off-site | National Grid Electricity Distribution |  | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | NGED | None | Developer not expected to pay for off-site reinforcement. Utility provider solely responsible for funding. | None currently identified | Unclear | Arup assessment against National Grid Electricity Distribution online Capacity Maps submitted for Phase 2 Addendum study - Autumn 2025
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Hinckley | On-site | Developer |  | 2031-2035 | Essential | 898938.3 | 898938.3 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Hinckley | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 1863077.2 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Hinckley | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 118188.94 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Hinckley | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 64723.6 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
| LPR138 | Land at Brick Kiln Street (the former Cadent site), Hinckley | 195 | 195 | TR35 | Transport | Active Travel | Cycling Infrastructure | Cycling Route A | Contained within JTE evidence. Further details to be provided in LCWIP. | Hinckley | Off-site | LCC | Developer | 2031-2035 | Essential | 1813660 | 1915969 | S106, Local Authority Funding | Developer contibution pooled with site AS173 expected to provide sufficient funding for scheme | Cost through S106 still to be apportioned to site | LCWIP hasn't been published. Priority of route unknown. Pooled contributions expected from sites which are no longer being taken forward. | High | JTE Study April 2026
[5 empty] | TR43 | Transport | Bus | Highway/Bus Service Infrastructure | Regent Street/The Borough - Removal of on-street parking on The Borough to make room for an additional Northbound Approach | Expected to mitigate the impact of additional traffic generation in areas where there are existing issues with delay and capacity | Hinckley | Off-site | LCC | Developer | 2031-2035 | Critical | 92405 | 92405 | S106 | Fully funded by developer | Due to low proposed cost this can be funded through S106 contribution | None currently identified | Unclear | Planning Application - Publicly available, JTE Report April 2026
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 111794 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Hinckley (likely Hinckley Gym Club, Richmond Park) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 86449 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 15131 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Hinckley (likely Hollycroft Park) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 6993 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Hinckley (likely Hollycroft Bowls Club) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 4184 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Hinckley | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 68250 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 395164.575 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 1394698.5 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 943929.09 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 186524.91 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 75941.6873 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2031-2035 | Critical | 101740.86 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 188760 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | NHS ICB indicated that local GP practices may struggle to accommodate the cumulative amount of growth planned across Hinckley, given existing challenges to expansion at those practices. | Medium | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | EL1 | Electric | Network upgrades | Off site reinforcement - Electricity | Upgrades to electricity network to service proposed development site | National Grid Electricity Distribution grid capacity assessment indicates that work will be required to service the proposed development site given current capacity constraints in the vicinity. | Hinckley | Off-site | National Grid Electricity Distribution |  | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | NGED | None | Developer not expected to pay for off-site reinforcement. Utility provider solely responsible for funding. | None currently identified | Unclear | Arup assessment against National Grid Electricity Distribution online Capacity Maps submitted for Phase 2 Addendum study - Autumn 2025
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Hinckley | On-site | Developer |  | 2031-2035 | Essential | 330741.45 | 330741.45 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Hinckley | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 676299 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Hinckley | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 55622.19 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Hinckley | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 28399.8 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
| LPR268 | Land Adjacent to the Ashby Canal, Hinckley | 150 | 150 | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Hinckley | On-site | Developer, Contractor | LCC | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Design Guide.
[5 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Hinckley | Off-site | Developer | LCC, National Highways, Warwickshire County Council | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[5 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Hinckley | On-site | Developer, Contractor | LCC | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[5 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Hinckley | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Hinckley | On-site and off-site | Leicestershire Police | HBBC | 2026-2030 | Desirable | 52500 | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding | Developer contribution towards other sources of funding | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2026-2030 | Critical | 303972.75 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2026-2030 | Critical | 1072845 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that a new 3FE primary school may be required to accommodate pupils from this development. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2026-2030 | Critical | 726099.3 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that a new 6FE secondary school may be required to accommodate pupils from this development. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2026-2030 | Critical | 143480.7 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that The Hinckley School may be expanded by around 100 places to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2026-2030 | Critical | 58416.6825 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Hinckley | Off-site | LCC |  | 2026-2030 | Critical | 78262.2 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2026-2030 | Critical | 145200 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | NHS ICB indicated that local GP practices may struggle to accommodate the cumulative amount of growth planned across Hinckley, given existing challenges to expansion at those practices. | Medium | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Hinckley | Off-site | Cadent Gas | HBBC, Developer | 2026-2030 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
[5 empty] | EL1 | Electric | Network upgrades | Off site reinforcement - Electricity | Upgrades to electricity network to service proposed development site | National Grid Electricity Distribution grid capacity assessment indicates that work will be required to service the proposed development site given current capacity constraints in the vicinity. | Hinckley | Off-site | National Grid Electricity Distribution |  | 2026-2030 | Critical | None | Cost subject to ongoing scoping and development | NGED | None | Developer not expected to pay for off-site reinforcement. Utility provider solely responsible for funding. | None currently identified | Unclear | Arup assessment against National Grid Electricity Distribution online Capacity Maps submitted for Phase 2 Addendum study - Autumn 2025
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Hinckley | On-site | Developer |  | 2026-2030 | Essential | 254416.5 | 254416.5 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Hinckley | On-site | HBBC / Local Parish |  | 2026-2030 | Essential | 520230 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Hinckley | Off-site | HBBC / Local Parish |  | 2026-2030 | Essential | 42786.3 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Hinckley | Off-site | HBBC / Local Parish |  | 2026-2030 | Essential | 21846 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
New Settlement | LPR235 | Lindley Meadows | 1604 | 3000 | TR41 | Transport | Active Travel | Cycling Infrastructure | Cycling Route N | Contained within JTE evidence. Further details to be provided in LCWIP. | New Settlement | Off-site | LCC | Developer | 2031-2035 | Essential | 23553373.46 | 24187219 | S106, Local Authority Funding | Developer contibution pooled with contribution from sites LPR168 and LPR192 expected to provide sufficient funding for scheme | Cost through S106 still to be apportioned to site | LCWIP hasn't been published. Priority of route unknown. Pooled contributions expected from sites which are no longer being taken forward. | High | JTE Study April 2026
[5 empty] | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | New Settlement | On-site | Developer, Contractor | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Design Guide.
[5 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | New Settlement | Off-site | Developer | LCC, National Highways, Warwickshire County Council | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[5 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | New Settlement | On-site | Developer, Contractor | LCC, National Highways, Warwickshire County Council | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[5 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | New Settlement | On-site and off-site | Developer, Contractor | LCC, Bus Operator, Warwickshire County Council | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | New Settlement | On-site and off-site | LCC |  | 2031-2035 | Critical | 6079455 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | New Settlement | On-site and off-site | LCC |  | 2031-2035 | Critical | 21456900 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that two new 2FE primary schools may be required to accommodate pupils from this development (one may be expanded to 3FE at a later date). | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | New Settlement | On-site and off-site | LCC |  | 2031-2035 | Critical | 14521986 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that a new 6FE secondary school may be required to accommodate pupils from this development. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | New Settlement | On-site and off-site | LCC |  | 2031-2035 | Critical | 2869614 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that if a new secondary school is built, this should contain post 16 provision to accommodate pupils from this development. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | New Settlement | On-site and off-site | LCC |  | 2031-2035 | Critical | 1168333.65 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | New Settlement | On-site and off-site | LCC |  | 2031-2035 | Critical | 1565244 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 917709 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 709660 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 124210 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 57408 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 34349 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S06 | Sports | Pitches | Pitches | Pitch provision (natural grass pitches only) - capital cost | In line with Sports England requirements, provision of pitches (total pitch capital cost) | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 443356 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S07 | Sports | Pitches | Pitch maintenance | Lifecycle cost for pitch maintenance per annum (applied across 10-year period) (natural grass pitches only) | In line with Sports England requirements, provision of costs for maintenance lifecycle (cost per annum of pitches) | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 86998 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Grass Pitch Maintenance Fund, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S08 | Sports | Pitches | Changing rooms | Provision of changing rooms for provided pitches (natural grass pitches only) | In line with Sports England requirements, provision of cost for changing rooms (total capital cost) | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 881951 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure (and/or new health infrastructure facility given location of proposed development) | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact. Given location of proposed development, new facility may be required in addition to or instead of extensions to existing nearby facilities. | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 2904000 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | Proposed quantum of development poses significant impact on practices. ICB would prefer not to support large expansion of surgeries in rural areas. Development of new facility may be considered given quantum of development proposed. | Medium | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | P02 | Policing |  | Policing and Community Safety Contributions | Fluid infrastructure approach to policing and community safety capacity needs proposed by Leicestershire Police with additional identified requirement for additional on-site mitigation (for example, early phase PCSOs and more intensive community safety measures). | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives as well as Community Support Officers. | New Settlement | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 1200000 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | New Settlement | Off-site | Cadent Gas | HBBC, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
[5 empty] | G02 | Gas | Network upgrades | Off site reinforcement - Medium Pressure Gas | Upgrades to medium pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | New Settlement | Off-site | Cadent Gas | HBBC, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
[5 empty] | WW01 | Wastewater | Network upgrades | Off site capacity upgrades - Sewerage | Upgrades to sewage treatment work and/or receiving sewerage network to service proposed development site | STW’s desktop review identified that the site’s known network constraints are a site of this size would likely cause an adverse impact on the nearby sewerage infrastructure and probably necessitate a capital scheme to mitigate network capacity risk. and that it is assumed to be able to connect to the local wastewater network by the site could connect to the PS - Fenny Drayton (SPS) to the west of the site, or due to the size of the site a new rising main to the Nuneaton Hartshill catchment could be required to ensure capacity risk is mitigated. | New Settlement | Off-site | Severn Trent Water | HBBC | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | Severn Trent Water | None | All network upgrade works required due to growth are funded through Severn Trent Water's Asset Management Programme (AMP) cycle. Developers are unlikely to be asked for a contribution. | None currently identified | Unclear | Severn Trent Water assessment of sewerage provision for proposed development sites submitted as part of this study
[5 empty] | EL1 | Electric | Network upgrades | Off site reinforcement - Electricity | Upgrades to electricity network to service proposed development site | National Grid Electricity Distribution have provided details of their electricity network in the area, and indicated that capacity is constrained and works will be required to service the proposed development sites. An in-depth assessment of local grid capacity may be carried out in conjunction with NGED to assess whether network upgrades can be avoided for LPR235 via use of existing supply point at Tamworth. | New Settlement | Off-site | National Grid Electricity Distribution |  | 2031-2035 | Critical | None | Cost subject to ongoing scoping and development | NGED | None | Developer not expected to pay for off-site reinforcement. Utility provider solely responsible for funding. | None currently identified | Unclear | Arup assessment against National Grid Electricity Distribution online Capacity Maps submitted for Phase 2 Addendum study - Autumn 2025
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | New Settlement | On-site | Developer |  | 2031-2035 | Essential | 5088330 | 5088330 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | New Settlement | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 11278440 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | New Settlement | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 0 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | New Settlement | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 0 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
Market Bosworth | LPR139 | Land South of Station Road (Phase 2), Market Bosworth | 200 | 200 | TR18 | Transport | Bus | Bus Service Provision | Extension of 153 bus service outside of the site. Should phase 2 come forwards, the service would be extended into the site | Cost around £170k for bus service outside of site. Consultation with LCC required for internal service | Market Bosworth | Off-site | LCC | Developer, Bus operator | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | N/A | Subject to ongoing discussions with the local bus operator (Arriva). | Low | Planning Application - Publicly available
[5 empty] | TR19 | Transport | Highways | Off-Site Carriageway Improvements | Currently, there is an existing 7.5 tonne (except for loading) weight restriction in force on Station Road immediately to the east of the existing industrial estate access. The Applicant is proposing to relocate the weight restriction to the east of the Kyngs Golf Club access and west of the junction of Godsons Hill with Station Road. | TRO required with contributions through S106 | Market Bosworth | Off-site | LCC | Developer | 2031-2035 | Critical | 7500 | 7500 | S106 | Fully funded by developer | N/A | None currently identified | Unclear | Planning Application - Publicly available
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | Market Bosworth | Off-site | LCC |  | 2031-2035 | Critical | 405297 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Market Bosworth | Off-site | LCC |  | 2031-2035 | Critical | 1430460 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated a 0.5FE expansion of St Peters may be required to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Market Bosworth | Off-site | LCC |  | 2031-2035 | Critical | 968132.4 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated Bosworth Academy may be expanded by 2FE to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Market Bosworth | Off-site | LCC |  | 2031-2035 | Critical | 191307.6 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Market Bosworth | Off-site | LCC |  | 2031-2035 | Critical | 77888.91 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Market Bosworth | Off-site | LCC |  | 2031-2035 | Critical | 104349.6 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that the relevant school is on a constrained site and would struggle to expand. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 114416 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 88477 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 15486 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Market Bosworth (likely Market Bosworth Tennis Club) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 7157 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Market Bosworth (likely Market Bosworth Bowls Club) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 4282 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Markfield | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 70000 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 193600 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | One of two nearby surgeries identified as not having space for expansion. The other applicable surgery can expand but would require travel from the proposed site. | Medium | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Market Bosworth | Off-site | Cadent Gas | HBBC, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Market Bosworth (Parish) | On-site | Developer |  | 2031-2035 | Essential | 339222 | 339222 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Market Bosworth (Parish) | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 693640 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Market Bosworth (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 57048.4 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Market Bosworth (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 29128 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
Markfield | LPR70 | Land East of Ratby Lane and South of Jacqueline Road, Markfield | 135 | 135 | TR32 | Transport | Active Travel | Off-Site Walking Infrastructure | Proposed pedestrian refuge on Launde Road close to the junction with Countryman Way | Enabling connection to bus facilities | Markfield | Off-site | Developer | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | N/A | None currently identified. Substantive response provided by LCC Highways on 13 February 2026 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR33 | Transport | Active Travel | Off-Site Walking Infrastructure | Tactile Paving provided for existing uncontrolled crossing at the junction between Launde Road and Rathby Road | Improving site connectivity | Markfield | Off-site | Developer | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | N/A | None currently identified. Substantive response provided by LCC Highways on 13 February 2026 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR34 | Transport | Highways | Off-site Junction Improvements | Proposed improvements to Field Head roundabout. | Site to contribute to A511 Growth Corridor scheme. | Markfield | Off-site | LCC | Developer | 2031-2035 | Critical | 659340 | Cost subject to ongoing scoping and development | S106, Local Authority / Central Government Funding | Developer contribution towards other sources of funding for wider scheme | £4884 Per dwelling | None currently identified. Substantive response provided by LCC Highways on 13 February 2026 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 273575.475 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 965560.5 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that a 0.5FE expansion at Mercenfield Primary School may be required to accommodate pupils from this development, however there are site constraints here. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 653489.37 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 129132.63 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 52575.0143 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 70435.98 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 77231 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 59772 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Markfield-vicinity (likely Groby/Brookvale Campus) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 10453 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 4831 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 2891 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 130680 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | NHS ICB did not consider corresponding GP facilities to face any significant deliverabiltiy challenges to expansion. | Low | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Markfield | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 47250 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Markfield (Parish) | On-site | Developer |  | 2031-2035 | Essential | 220494.3 | 220494.3 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Markfield (Parish) | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 450866 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Markfield (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 37081.46 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Markfield (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 18933.2 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
| LPR94 A | Land South of London Road (Site A), Markfield | 170 | 170 | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 164560 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | NHS ICB did not consider corresponding GP facilities to face any significant deliverabiltiy challenges to expansion. | Low | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 344502.45 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 1215891 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that a 0.5FE expansion at Mercenfield Primary School may be required to accommodate pupils from this development, however there are site constraints here. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 822912.54 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 162611.46 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 66205.5735 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 88697.16 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 97253 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 75206 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Markfield-vicinity (likely South Charnwood Academy) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 13163 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 6084 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Markfield-vicinity (likely Bagworth Bowls Club) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 3640 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Markfield | Off-site | Cadent Gas | HBBC, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Markfield (Parish) | On-site | Developer |  | 2031-2035 | Essential | 288338.7 | 288338.7 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Markfield (Parish) | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 589594 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Markfield (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 48491.14 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Markfield (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 24758.8 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | WW01 | Wastewater |  | Off site capacity upgrades - Sewerage | Upgrades to sewage treatment works and/or receiving sewerage network to service proposed development site | Severn Trent Water have undertaken as assessment of capacity in the area; however no details have been provided on where upgrade works are required. Developer contribution to upgrade works will be required, but this will need to be discussed further with Severn Trent Water. | Markfield | Off-site | LCC | Developer | 2031-2035 | Essential | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | N/A | None currently identified | Unclear | S106 agreement for 20/01283/FUL
[5 empty] | TR50 | Transport | Highways | Off Site Carriageway Improvements | A50 Field Head Roundabout Improvements | Site to contribute to A511 Growth Corridor scheme. | Markfield | Off-site | LCC | Developer | 2031-2035 | Critical | 1377288 | Cost subject to ongoing scoping and development | S106, Local Authority Funding | Developer contribution towards other sources of funding for wider scheme | £4884 cost per dwelling factor applied | None currently identified. Highways contribution agreed in conjunction with planning consent 22/01153/DOV. | Low | Planning Application - Publicly available
[5 empty] | TR51 | Transport | Highways | Bus infrastructure | Bus stops in vicinity of the site to be improved to include real time information and bus boarder kerbs. | Required due to increased public transport trips from the site | Markfield | Off-site | LCC | Developer, Bus operator | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | N/A | None currently identified | Low | Planning Application - Publicly available
[5 empty] | TR57 | Transport | Active Travel | Footway/cycleway Provision | • New footway links to connect the proposed development to existing facilities on London Road and Dr Wright Close • New foot/cycle link to Croftway • New footpaths within the site to link to existing footpaths and public rights of way • Uncontrolled pedestrian crossing facilities at the London Road/Croftway/Main Street junction | Required to mitigate proposed walking/cycling trips | Markfield | On-site and off-site | Developer | LCC | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S278 | Fully funded by developer | Costs not yet develooped for the described scheme | None currently identified | Low | Planning Application - Publicly available
| LPR94 B | Land South of London Road and West of Ratby Lane (Site B), Markfield | 95 | 95 | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Newbold Verdon | On-site | Developer, Contractor | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Design Guide.
[5 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Newbold Verdon | Off-site | Developer | LCC, National Highways, Warwickshire County Council | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[5 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Newbold Verdon | On-site | Developer, Contractor | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[5 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Newbold Verdon | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 679468.5 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that Desford Primary School may be expanded by 1FE to make it a 3FE school to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 459862.89 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated Bosworth Academy may be expanded by 2FE to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Markfield | Off-site | LCC |  | 2031-2035 | Critical | 90871.11 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated Bosworth Academy (post 16 provision) may be expanded by approximately 100 places to accommodate pupils from this development, if needed. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 54586 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 42211 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Markfield-vicinity (likely Groby/Brookvale Campus) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 7388 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 3415 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Markfield-vicinity (likely Bagworth Bowls Club) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 2043 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 91960 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | NHS ICB did not consider corresponding GP facilities to face any significant deliverabiltiy challenges to expansion. | Low | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Markfield | Off-site | Cadent Gas | HBBC, Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Markfield (Parish) | On-site | Developer |  | 2031-2035 | Essential | 161130.45 | 161130.45 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Markfield (Parish) | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 329479 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Markfield (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 27097.99 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Markfield (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 13835.8 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Newbold Verdon | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 33250 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
Newbold Verdon | LPR190 | Land South of Arnolds Crescent, Newbold Verdon | 135 | 135 | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Newbold Verdon | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 47250 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | E01 | Education | Early Years | Early Years Contribution | Contributions to Early Years capacity expansion | Early years contribution agreed upon in planning agreements for the site. | Newbold Verdon | Off-site | LCC |  | 2031-2035 | Critical | 210635.1 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S110 | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | S106 agreement for 24/01558/OUT
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Newbold Verdon | Off-site | LCC |  | 2031-2035 | Critical | 965560.5 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated a 0.5FE expansion of Newbold Verdon Primary School may be required to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Newbold Verdon | Off-site | LCC |  | 2031-2035 | Critical | 653489.37 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated Bosworth Academy may be expanded by 2FE to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Newbold Verdon | Off-site | LCC |  | 2031-2035 | Critical | 129132.63 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated post 16 pupils yielded here should be considered in the expansion of Bosworth Academy. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Newbold Verdon | Off-site | LCC |  | 2031-2035 | Critical | 52575.0143 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Newbold Verdon | Off-site | LCC |  | 2031-2035 | Critical | 70435.98 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 77469 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 59906 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Newbold Verdon (likely Newbold Verdon Playing Fields) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 10485 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Newbold Verdon (likely Market Bosworth Lawn Tennis Club) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 4846 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 2900 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | OS3 | Open Space | Provision of Open Space | Open Space | Off Site Open Space Contribution | Towards the provision and / or improvement of new of existing outdoor sports facilities within 1km of the development land to a maximum of £46,915.20 (plus maintenance) calculated by dwellings x 38.4 sqm x £9.05 | Newbold Verdon | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 46915.2 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106 | Developer contribution towards other sources of funding for wider scheme |  | None currently identified | Unclear | S106 agreement for 24/01158/OUT
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 104544 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Cost to site developer extracted from latest planning agreement with HBBC (see Sources for further information) NHS ICB analysis as part of stakeholder engagement for this study suggested site contribution of £130,680 | Existing applicable surgeries have limited spare capacity. Proposed development across Market Bosworth and Desford would pose challenges for meeting new demand. | Medium | Planning agreement…..t accessed at, https://publicdocuments.hinckley-bosworth.gov.uk/PublicAccess_LIVE/Document/ViewDocument?id=8B2EFCE9F0CC4D4AA6EFFE16C60DF23B and Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | WA1 | Waste |  | Waste services contributions | Contribution towards waste facilities resulting from increased demand for services from site development (unspecified) | £49.53 per dwelling up to a maximum of £6,686.55 | Newbold Verdon | Off-site | HBBC and LCC |  | 2031-2035 | Critical | 6686.55 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, central government, EPR scheme | Developer contribution towards other sources of funding for wider scheme | Planning agreement identifies factor cost contribution towards waste of £49.53 per dwelling up to a maximum of £6,686.55 | None currently identified | Unclear | S106 agreement for 24/01158/OUT
[5 empty] | TR20 | Transport | Active Travel | Off-Site Footway Improvements | Appropriate resurfacing of public footpath S26 and street lighting provision. As well as Improvements to surfacing, waymarking and lighting for public footpath R29 within the sit. Improvements to surfacing, waymarking and lighting for public footpath R4 within the site and minor diversion of route through the site | Contribution defined within agreed S106 | Newbold Verdon | On-site | LCC | Developer | 2031-2035 | Critical | 64306 | 64306 | S106 | Fully funded by developer | N/A | None currently identified. To be delivered in accordance with planning consent 24/01158/OUT. | Low | Planning Application - Publicly available
[5 empty] | TR21 | Transport | Highways | Off Site Carriageway Improvements | Extension of 30mph speed limit across site access on Brascote Lane | Traffic Regulation Order required with contributions through S106 | Newbold Verdon | Off-site | LCC | Developer | 2031-2035 | Critical | 7500 | 7500 | S106 | Fully funded by developer | TRO cost defined within LCC highways reponse | None currently identified. Substantive response provided by LCC Highways on 11 December 2025 with draft conditions. | Low | Planning Application - Publicly available
| LPR207 | Land North West of Old Farm Lane and South of Bosworth Lane, Newbold Verdon | 200 | 200 | TR26 | Transport | Highways | Off-site Junction Improvements | Bull in the Oak Junction Improvements - Upgrade to a signalised junction | Proposed as a result of pressure on junction and other local developments | Newbold Verdon | Off-site | LCC | Developer | 2031-2035 | Critical | 607296 | £1.5-£2million | S106, Local Authority Funding | Developer contribution towards other sources of funding for wider scheme | Cost defined in S106 Agreement | None currently identified. Substantive response provided by LCC Highways on 11 December 2025 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR27 | Transport | Active Travel | Off-Site Walking Infrastructure | Public Footpath S19 improvements | Contribution required from developer | Newbold Verdon | Off-site | LCC | Developer | 2031-2035 | Critical | 89785 | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | Cost defined in S106 Agreement | None currently identified. Substantive response provided by LCC Highways on 11 December 2025 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR28 | Transport | Active Travel | Off-Site Walking Infrastructure | Footpath Construction along Bosworth Lane | Required to access existing footway provision | Newbold Verdon | Off-site | Developer | LCC | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S278 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 11 December 2025 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 114416 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 88477 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Newbold Verdon (likely Newbold Verdon Playing Fields) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 15486 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Newbold Verdon (likely Market Bosworth Lawn Tennis Club) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 7157 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 4282 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | Newbold Verdon | Off-site | LCC |  | 2031-2035 | Critical | 405297 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Newbold Verdon | Off-site | LCC |  | 2031-2035 | Critical | 1430460 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated a 0.5FE expansion of Newbold Verdon Primary School may be required to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Newbold Verdon | Off-site | LCC |  | 2031-2035 | Critical | 968132.4 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated Bosworth Academy may be expanded by 2FE to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Newbold Verdon | Off-site | LCC |  | 2031-2035 | Critical | 191307.6 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated post 16 pupils yielded here should be considered in the expansion of Bosworth Academy. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Newbold Verdon | Off-site | LCC |  | 2031-2035 | Critical | 77888.91 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Newbold Verdon | Off-site | LCC |  | 2031-2035 | Critical | 104349.6 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Ratby | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 70000 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Newbold Verdon (Parish) | On-site | Developer |  | 2031-2035 | Essential | 339222 | 339222 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Newbold Verdon (Parish) | On-site | HBBC / Local Parish |  | 2031-2035 | Essential | 693640 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Newbold Verdon (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 57048.4 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Newbold Verdon (Parish) | Off-site | HBBC / Local Parish |  | 2031-2035 | Essential | 29128 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
Ratby | LPR107 | Land South of Markfield Road, Ratby | 470 | 470 | TR42 | Transport | Active Travel | Cycling Infrastructure | Cycling Route AB | Contained within JTE evidence. Further details to be provided in LCWIP. | Ratby | Off-site | LCC | Developer | 2031-2035 | Essential | 11176620 | 12391471 | S106, Local Authority Funding | Developer contribution pooled with contribution from sites LPR196 and LPR134 expected to provide sufficient funding for scheme | Cost through S106 still to be apportioned to site | LCWIP hasn't been published. Priority of route unknown. Pooled contributions expected from sites which are no longer being taken forward. | Medium | JTE Study April 2026
[5 empty] | TR22 | Transport | Highways | Off-site Junction Improvements | Desford Lane Junction Improvement Scheme - Junction to be upgraded to a signalised junction | Contribution still to be agreed through S106 | Ratby | Off-site | LCC | Developer | 2031-2035 | Critical | Information not yet available | 12407711 | S106, Local Authority Funding | Developer contribution towards other sources of funding for wider scheme | Funded through a mix of S106 contributions from other sites | None currently identified. Substantive response provided by LCC Highways on 19 December 2025 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR23 | Transport | Highways | Off-site Junction Improvements | Groby Road/Sacheverell Way Junction Improvement Scheme - Junction to be upgraded to a signalised junction | Contribution still to be agreed through S106 | Ratby | Off-site | LCC | Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106, Local Authority Funding | Developer contribution towards other sources of funding for wider scheme | Subject to scope | Substantive response provided by LCC Highways on 19 December 2025 with draft conditions. National Highways holding objection 3 September 2025 requesting further information. | Medium | Planning Application - Publicly available
[5 empty] | TR24 | Transport | Bus | Bus Stop Infrastructure | Potential to contribute towards Arriva Service 28 | Will help to fill gaps in service locally | Ratby | Off-site | LCC | Developer, Bus operator | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | Subject to negotiation with operator | None currently identified. Substantive response provided by LCC Highways on 19 December 2025 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | TR25 | Transport | Active Travel | Off-Site Walking Infrastructure | Scope to upgrade PRoW within the area | No exact scheme proposed at this stage | Ratby | Off-site | LCC | Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | Subject to scope | None currently identified. Substantive response provided by LCC Highways on 19 December 2025 with draft conditions. | Low | Planning Application - Publicly available
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 268877 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 207921 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Ratby-vicinity (likely Groby/Brookvale Campus) | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 36392 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 16820 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2031-2035 | Essential | 10064 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | Ratby | Off-site | LCC |  | 2031-2035 | Critical | 952447.95 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Ratby | On-site and off-site | LCC |  | 2031-2035 | Critical | 3361581 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | LCC have indicated that a new 1FE primary school will be part as part of this development which may not be needed until around 2035 as there is surplus in existing primary schools until this point. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Ratby | Off-site | LCC |  | 2031-2035 | Critical | 2275111.14 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that a 1FE expansion of Brookvale Groby Learning Campus is likely to be required to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Ratby | Off-site | LCC |  | 2031-2035 | Critical | 449572.86 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | Ratby | Off-site | LCC |  | 2031-2035 | Critical | 183038.9385 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | Ratby | Off-site | LCC |  | 2031-2035 | Critical | 245221.56 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2031-2035 | Critical | 454960 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | Existing applicable surgeries have limited spare capacity. Proposed development across Market Bosworth and Desford would pose challenges for meeting new demand. | Medium | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Thornton | On-site and off-site | Leicestershire Police | HBBC | 2031-2035 | Desirable | 164500 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
Thornton | AS33 | Land off Warwick Close, St Peters Drive and Sharp's Close, Thornton | 60 | 60 | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Thornton | On-site | Developer, Contractor | LCC | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Design Guide.
[5 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Thornton | Off-site | Developer | LCC, National Highways, Warwickshire County Council | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[5 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Thornton | On-site | Developer, Contractor | LCC | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[5 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Thornton | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[5 empty] | P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | Thornton | On-site and off-site | Leicestershire Police | HBBC | 2026-2030 | Desirable | 21000 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding for wider scheme | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
[5 empty] | S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2026-2030 | Essential | 34324 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2026-2030 | Essential | 26543 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2026-2030 | Essential | 4646 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2026-2030 | Essential | 2147 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | Borough-wide or vicinity | Off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | 2026-2030 | Essential | 1285 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
[5 empty] | E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | Thornton | Off-site | LCC |  | 2026-2030 | Critical | 429138 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated that Thornton Primary School is just over 0.5FE and its capacity is due to have a small deficit of places by 2030. This cannot be expanded due to a constrained site. | Medium | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | Thornton | Off-site | LCC |  | 2026-2030 | Critical | 290439.72 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | LCC have indicated a 0.5-1FE expansion of South Charnwood High School may be required to accommodate pupils from this development. | Low | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | Thornton | Off-site | LCC |  | 2026-2030 | Critical | 57392.28 | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | None currently identified | Unclear | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
[5 empty] | HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | Vicinity GP surgeries | Off-site | NHS ICB | HBBC | 2026-2030 | Critical | 58080 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | NHS ICB did not consider corresponding GP facilities to face any significant deliverabiltiy challenges to expansion. | Low | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
[5 empty] | OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Bagworth and Thornton (Parish) | On-site | Developer |  | 2026-2030 | Essential | 101766.6 | 101766.6 | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | Bagworth and Thornton (Parish) | On-site | HBBC / Local Parish |  | 2026-2030 | Essential | 208092 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | Bagworth and Thornton (Parish) | Off-site | HBBC / Local Parish |  | 2026-2030 | Essential | 17114.52 | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
[5 empty] | OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | Bagworth and Thornton (Parish) | Off-site | HBBC / Local Parish |  | 2026-2030 | Essential | 8738.4 | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
Leicestershire-wide infrastructure |  |  |  |  | TR44 | Transport | Multi Modal | Mobility Hub | Proposed Hinckley Train Station Mobility Hub | Proposed to facilitate modal interchange as a result of development | Hinckley | Off-site | LCC | Network Rail | 2036-2040 | Desirable | Information not yet available | 1124855 | Active Travel England, Developer contributions | None | Only initially costed at this point | No funding secured at the time of publication. Amount of funding required of considerable scale. | High | JTE Study April 2026
[5 empty] | TR53 | Transport | Multi Modal | Mobility Hub | Proposed East Shilton Mobility Hub | Proposed to facilitate modal interchange as a result of development | East Shilton | Off-site | LCC | Network Rail | 2036-2040 | Desirable | Information not yet available | 571817 | Active Travel England, Developer contributions | None | Only initially costed at this point | No funding secured at the time of publication. Amount of funding required of considerable scale. | High | JTE Study April 2026
[5 empty] | TR54 | Transport | Highways | Off Site Junction mitigation | Modelling of the additional allocations may result in additional mitigation being identified. To be confirmed upon completion of further JTE modelling to assess the impact of the additional Local Plan allocations on the highway network. | Current evidence base of the South Leicestershire JTE, does not reflect all of the allocations | Regional | Off-site | LCC | Contractor | 2026-2045 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, central government | Developer contribution towards other sources of funding for wider scheme | N/A | None currently identified | High | Information to be published in Summer 2026
[5 empty] | TR46 | Transport | Rail | Midlands Rail Hub | Midlands Rail Hub - upgrades to the existing lines around Birmingham which will see an increase in capacity on services serving and passing through Hinckley | SOBC funded by DfT. No scheme funding for east section. | Regional | Off-site | Network Rail (To become Great British Rail from April 2027) | DFT | 2031-2045 | Regionally-critical infrastructure necessitated beyond Local Plan process | None | £1.75 billion | Central Government | Scheme reliant on significant capital funding from central government, beyond the scale of developer contributions | No proposed date for funding to be allocated | Proposals for the East Midlands area are unfunded and have no certainty | High | Derived from discussions with Midlands Connect
[5 empty] | TR45 | Transport | Bus | Bus Service | Bus service and infrastructure contribution in line with Leicestershire Planning Obligations Policy Appendix A: Highways and Transportation. Bus Stops to be constructed to LCC Highway Standards, where upgrading/relocation of existing bus stops is required. | LCC highways to advise where this is required on a site by site basis. | Regional | On-site | LCC | Developer, Contractor | 2026-2045 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106, Local Authority Funding | Developer contribution towards other sources of funding for wider scheme |  | None currently identified | Low | LCC Highways Development Management (HDM) Policy 1.
[5 empty] | TR55 | Transport | Highways | Highway Improvements | A5 Dodwells to Longshoot Improvement Scheme | Extracted from the RIS3/RIS4 Pipeline | Hinckley | Off-site | National Highways | LCC | 2026-2045 | Desirable | Information not yet available | Cost subject to ongoing scoping and development | Central Government | Developer contribution towards other sources of funding for wider scheme | To be developed in RIS 3 (2026-2031) for construction in RIS4 (2031-2036) | Scheme still needs to be designed and costed and will need to be included in the Route Investment Strategy for Road Period 4. | High | Road Investment Strategy 3 (RIS3) 2026 to 2031 (March 2026)
[5 empty] | TR56 | Transport | Highways | Highway Improvements | A5 Concept Link Scheme | Scheme to connect the A47 and A5 to the west of Hinckley | Hinckley | Off-site | LCC | National Highways, Canal and River Trust | 2026-2045 | Regionally-critical infrastructure necessitated beyond Local Plan process | Information not yet available | Cost subject to ongoing scoping and development | Central Government, Local Authority | Developer contribution towards other sources of funding for wider scheme | Scheme presented to LCC Cabinet on 12 September 2025. Recommendation to consult with HBBC to support work on the Local Plan and to continue to develop the scheme. | Scheme will require viability assessment, detailed design, a business case to demonstrate value for money and investment from Central Government to be deliverable. | High | Wider discussions with stakeholders including HBBC, LCC and WCC. LCC Committee report accessed at https://democracy.leics.gov.uk/documents/s191532/Final%20A5%20Concept%20Cabinet%20Report%20120925.pdf
[5 empty] | TR58 | Transport | Rail | Coventry - Leicester - Nottingham Rail Service | Reinstatement of direct rail services between Coventry, Leicester and Nottingham | Reduction in passenger journey times | Regional | Off-site | Midlands Connect | LCC | 2026-2045 | Regionally-critical infrastructure necessitated beyond Local Plan process | Information not yet available | Cost subject to ongoing scoping and development | Central Government | Scheme reliant on significant capital funding from central government, beyond the scale of developer contributions | Midlands Connect submitted a Strategic Outline Business Case to the Department for Transport in Spring 2025 and should this be successful, the next stage will be the submission of an Outline Business Case. | Scheme requires more detailed work on the engineering aspects of the project, as well as further investigation into the benefits. | High | https://www.midlandsconnect.uk/media/saxnvkbw/midlands-connect-coventry-to-leicester-passengers-report.pdf
[5 empty] | TR59 | Transport | Rail | Nuneaton Parkway | New P&R station at Nuneaton Parkway - location TBC | Midlands Connect have identified Nuneaton Parkway as a priority scheme in their recent Strategic Park and Ride study and concluded that the station (along with improved services) is likely to help intercept vehicle trips from the Strategic Road Network and thereby contribute to a reduction in car mileage/carbon and town/city centre congestion. | Regional | Off-site | Midlands Connect | WCC | 2026-2045 | Regionally-critical infrastructure necessitated beyond Local Plan process | Information not yet available | Cost subject to ongoing scoping and development | Central Government | Scheme reliant on significant capital funding from central government, beyond the scale of developer contributions | The County Council will undertake a refresh of the high-level business case viability before carrying out a more significant piece of work to produce a Strategic Outline Business Case (SOBC) for the scheme. It is anticipated that this update along with the work to develop the SOBC will be undertaken in 2026/27. | Warwickshire County Council has undertaken a high-level feasibility study to ascertain if the station is likely to have a positive Business Case. A range of site options have been identified where the station could be located, this approach has included an assessment of the ‘long’ list of sites to determine a preferred location. | High | https://www.rugby.gov.uk/documents/20124/6836086/Nuneaton+Parkway+Safeguarding+document.pdf/bfd7301b-6569-43fa-e570-67eec48fc1ca?t=1767878673573
[5 empty] | SC1 | Social and Care Services | Extra Care | Extra Care facilities | New and/or expanded extra care facilities in Leicestershire and bordering counties accessible for residents of Hinckley & Bosworth | New and/or extra care facilities are required to accommodate cumulative growth from all new sites | Regional | Off-site | Private developer of care homes | LCC, HBBC | 2026-2045 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Private provider, LCC, HBBC | None | New and/or expanded Extra Care facilities are typically paid for by private providers, who are reliant on LCC and HBBC funds to support residents in these car facilities. Developers of new housing sites are not expected to contribute to this infrastructure. | LCC in their engagement for this study suggested there were no outstanding obstacles to the delivery of extra care facilities across Leicestershire of note and worth highlighting in this study | Low | Stakeholder engagement with LCC Strategic Services (Adults & Communities)

## Employment
Settlement | Site ref | Site name | Area of emp land (ha) | Floorspace deliverable in plan period (2020 - 2045) m2 | Strategic B8 / General Emp (class E, B2 and non - strategic B8) / Mix (General and Strategic B8) | Scheme Reference ID | Topic | Sub Topic | Project Name | Project Description | Project Notes | Settlement | On-site / Off-site | Delivery body | Other key stakeholder(s) or delivery bodies | Delivery Period | Priority | Cost apportioned to site | Estimated cost of total scheme | All funding sources for total scheme | Developer contribution towards expected funding gap | Cost Notes | Deliverability challenges | Implementation difficulty | Source(s)
Burbage | LPR241 | Land at Start Farm, Burbage | 7.1 | 23543 | General Emp | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Design Guide.
[6 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | Off-site | Developer | LCC, National Highways | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[6 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[6 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[6 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Burbage | Off-site | Cadent Gas | HBBC, Developer | 2026-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Information not yet available | Developer contribution will be ascertained at planning application stage. | None identified | Low | Cadent Gas analysis submitted to study (May 2026)
| LPR16A | Land South of Soar Brook, Burbage | 117.38 | 325160 | Strategic B8 / Mix | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Design Guide.
[6 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | Off-site | Developer | LCC, National Highways | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[6 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[6 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[6 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Burbage | Off-site | Cadent Gas | HBBC, Developer | 2026-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Information not yet available | Developer contribution will be ascertained at planning application stage. | None identified | Low | Cadent Gas analysis submitted to study (May 2026)
[6 empty] | G02 | Gas | Network upgrades | Offsite reinforcement - Medium Pressure Gas Network | Upgrades to medium pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Burbage | Off-site | Cadent Gas | HBBC, Developer | 2026-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Information not yet available | Developer contribution will be ascertained at planning application stage. | None identified | Low | Cadent Gas analysis submitted to study (May 2026)
| LPR259 | Land East of Hinckley Park, Burbage | 35.82 | 92903 | Strategic B8 / Mix | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Design Guide.
[6 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | Off-site | Developer | LCC, National Highways | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[6 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[6 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[6 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Burbage | Off-site | Cadent Gas | HBBC, Developer | 2026-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Information not yet available | Developer contribution will be ascertained at planning application stage. | None identified | Low | Cadent Gas analysis submitted to study (May 2026)
[6 empty] | G02 | Gas | Network upgrades | Offsite reinforcement - Medium Pressure Gas Network | Upgrades to medium pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Burbage | Off-site | Cadent Gas | HBBC, Developer | 2026-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Information not yet available | Developer contribution will be ascertained at planning application stage. | None identified | Low | Cadent Gas analysis submitted to study (May 2026)
| LPR44 | Land adjoining Hinckley Waste Water Treatment Works (WWTW), Brookfield Road, Burbage | 10.64 | 40000 | General Emp | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Design Guide.
[6 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | Off-site | Developer | LCC, National Highways | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[6 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[6 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Burbage | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[6 empty] | TR37 | Transport | Active Travel | Walking/Cycling Infrastructure | Cycling Route D | Shared with the consultant as part of the JTE study due to no LCWIP being produced as of yet. Further details of mitigations to be published in LCWIP | Burbage | Off Site | LCC | Developer | 2026-2035 | Critical | 1688347 | 1688347 | S106 | Fully funded by site |  | No planning application so will need to be negotiated during planning process | Low | JTE Study April 2026
Bagworth | LPR243 (previously EMP1) | Land at Wiggs Farm, Wood Lane/Station Road, Bagworth | 11 | 39000 | General Emp | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Bagworth | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Design Guide.
[6 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Bagworth | Off-site | Developer | LCC, National Highways | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[6 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Bagworth | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[6 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Bagworth | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[6 empty] | G02 | Gas | Network upgrades | Offsite reinforcement - Medium Pressure Gas Network | Upgrades to medium pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Bagworth | Off-site | Cadent Gas | HBBC, Developer | 2026-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Information not yet available | Developer contribution will be ascertained at planning application stage. | None currently identified | Low | Cadent Gas analysis submitted to study (May 2026)
Hinckley | LPR22 | Land at Wapping and Harrow Farm, Watling Street (A5), Hinckley | 47.51 | 152640 | Strategic B8 | TR15 | Transport | Highways | Off-site Junction Improvements | A5/Dodwells Junction Improvement Scheme - Additional Lane on Dodwells Road | Contribution defined within agreed S106 | Hinckley | Off-site | LCC | Developer | 2031-2035 | Critical | 1901750 | 1901750 | S106 contributions from multiple sites | S106 contributions from multiple sites | Cost derived from the JTE study report. | None currently identified | Medium | JTE Study April 2026
[6 empty] | TR36 | Transport | Active Travel | Cycling Infrastructure | Cycling Route C | Contained within JTE evidence. Further details to be provided in LCWIP. | Hinckley | Off-site | LCC | Developer | 2031-2035 | Critical | 925757 | 925757 | S106, Local Authority | Fully funded by developer | To be funded by LPR22 according to JTE Costing Mitigation Report | LCWIP hasn't been published. Priority of route unknown. | Low | JTE Study April 2026
[6 empty] | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Hinckley | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Design Guide.
[6 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Hinckley | Off-site | Developer | LCC, National Highways | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[6 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Hinckley | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[6 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Hinckley | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[6 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Hinckley | Off-site | Cadent Gas | HBBC, Developer | 2026-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Information not yet available | Developer contribution will be ascertained at planning application stage. | None identified | Low | Cadent Gas analysis submitted to study (May 2026)
Markfield | LPR95 | Land at Cliffe Hill Farm (Junction 22), Markfield | 28.3 | 65032 | Strategic B8 | TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Markfield | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Design Guide.
[6 empty] | TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Markfield | Off-site | Developer | LCC, National Highways | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
[6 empty] | TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Markfield | On-site | Developer, Contractor | LCC | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
[6 empty] | TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | Markfield | On-site and off-site | Developer, Contractor | LCC, Bus Operator | 2026-2045 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4.
[6 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Markfield | Off-site | Cadent Gas | HBBC, Developer | 2026-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Information not yet available | Developer contribution will be ascertained at planning application stage. | None identified | Low | Cadent Gas analysis submitted to study (May 2026)
Earl Shilton SUE | AS237 | Earl Shilton SUE | 5.3 | 53000 | not specified but likely to be general employment | TR13 | Transport | Bus | Enhancement of number 1 bus service | The enhanced 1 service will offer an increased frequency | This is a temporary measure until internal spine road completed upon which a new bus service will run through site | Earl Shilton | On-site | LCC | Bus Operator, Developer | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Information not yet available | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified through substantive response provided by LCC Highways on 17 May 2024 with draft conditions. | Low | Planning Application - Publicly available
[6 empty] | TR14 | Transport | Active Travel | Internal Walking and Cycling routes | An extensive network of shared use walking and cycling routes within the site which also connect to the existing external network, including Astley Road, Masefield Road, Mill Lane, Breach Lane and Avenue South; complemented by wayfinding | Tie into existing | Earl Shilton | On-site | Developer | Developer | 2026-2030 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified through substantive response provided by LCC Highways on 17 May 2024 with draft conditions. | Low | Planning Application - Publicly available
[6 empty] | TR16 | Transport | Active Travel | Off Site Pedestrian/cyclist improvement | Construction of a footway/cycleway on the A47 between the Leicester Road/Clickers Way roundabout and the junction of Desford Crossroads | n/a | Earl Shilton | Off-site | Developer | Developer | 2026-2030 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S278 | Information not yet available | Scheme has not been submitted to planning yet | None currently identified. Substantive response provided by LCC Highways on 17 May 2024 with draft conditions. | Low | Planning Application - Publicly available
[6 empty] | TR22 | Transport | Highways | Off-site Junction Improvements | Desford Lane Junction Improvement Scheme - Junction to be upgraded to a signalised junction | Contribution agreed through S106 | Earl Shilton | Off-site | LCC | Developer | 2026-2030 | Critical | 3548891 | 12408711 | S106, Local Authority | S106 contributions from multiple sites | East Shilton SUE is liable for 28.6% of growth within junction hence how this has been calculated | None currently identified. Substantive response provided by LCC Highways on 17 May 2024 with draft conditions. | Low | Planning Application - Publicly available
[6 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Earl Shilton | Off-site | Cadent Gas | HBBC, Developer | 2026-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Information not yet available | Developer contribution will be ascertained at planning application stage. | None identified | Low | Cadent Gas analysis submitted to study (May 2026)
[6 empty] | G02 | Gas | Network upgrades | Offsite reinforcement - Medium Pressure Gas Network | Upgrades to medium pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Earl Shilton | Off-site | Cadent Gas | HBBC, Developer | 2026-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Information not yet available | Developer contribution will be ascertained at planning application stage. | None identified | Low | Cadent Gas analysis submitted to study (May 2026)
Barwell SUE | AS58 | Barwell SUE | 6.2 | 24800 | not specified but likely to be general employment | TR04 | Transport | Bus | Enhancement of number 2 bus service | The enhanced 2 service will compliment the existing service between Barwell and Hinckley, and provide further connections to Hinckley rail station which will make use of the proposed improvements to the rail station and creation of a public transport interchange. | The enhancement of this service will align with the phasing of the development, with a 30 minute frequency service (one additional bus) being provided at occupation of 1,250 dwellings, and the 20 minute frequency service being provided at full occupation. | Barwell | Off-site | Developer, Bus Operator | LCC | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Information not yet available | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified through substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[6 empty] | TR05 | Transport | Bus | Bus Stop Construction | Bus stops to be constructed along Stapleton Lane which is along the 159 Route | Exact locations to be confirmed upon engagement with stakeholders | Barwell | Off-site | LCC | Bus Operator, Developer | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Information not yet available | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified through substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[6 empty] | TR06 | Transport | Bus | Bus Stop Construction | Bus stops to be constructed internally within the site within 400m walking distance of occupiers, with shelters, raised kerbing, bus service information | Subject to masterplan design principles | Barwell | On-site | Developer | Bus Operator, Developer | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Information not yet available | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified through substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[6 empty] | TR07 | Transport | Bus | Bus service information | A financial contribution can be made to the provision of public transport infrastructure and the implementation of Real Time Passenger Information (RTPI). | Funding will be provided for a set period following full occupation in order to assist the service in reaching commerciality. | Barwell | Off-site | LCC | Developer | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Information not yet available | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified through substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[6 empty] | TR08 | Transport | Active Travel | Internal Walking and Cycling routes | Within the site, a series of shared footway / cycle tracks will be provided along with retention/diversion of existing walk routes, as indicated below. The principles of these include: - Partial diversion of the public footpath no. U36 forming part of the Leicestershire Round to within a landscaped area; - A new footpath/ cycle path along the western edge of the site connecting PROW T99 and T58; - Retention and/or minor diversions of the following PROWs, U33, U35, T58, T97 and T99; - A new footpath/ cycle path from PROW U36, the Leicestershire Round, to Hinckley Road to the south west of the site; and - Retention and partial diversion of existing public footpaths within the site, which link to Mill Street, Moat Way, and Hereford Close / Galloway Close | To be designated within site masterplan | Barwell | On-site | Developer, Contractor |  | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Information not yet available | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified through substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[6 empty] | TR09 | Transport | Active Travel | Connection to Public right of way | There is also potential to upgrade the existing PROWs in Barwell to provide enhanced pedestrian and cycle connectivity for existing and future residents of Barwell and Barwell SUE. | No exact scheme proposed at this stage | Barwell | Off-site | LCC | Developer | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Information not yet available | Developer contribution will be ascertained as scheme scope develoed and at planning application stage. | None currently identified through substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[6 empty] | TR10 | Transport | Active Travel | Production of Framework Travel Plan | Applicant to appoint a travel plan coordinator to enforce the proposals within the Framework Travel Plan | The Framework Travel Plan would remain a ‘living document’, that will evolve and be updated by the Framework Travel Plan Coordinator to respond to local traffic conditions and opportunities for sustainable transport promotion, including schemes being implemented by the local highway authority and local transport stakeholders including bus operators. | Barwell | Off-site | Developer |  | 2031-2035 | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contribution | Fully funded by developer | Total contribution towards: - A5 Longshoot / Dodwells - Desford Crossroads junction improvement - Public Right of Way Improvements as detailed within the submitted documents - Ashby Road / Normandy Way junction improvement - Travel Packs - Travel Plan Monitoring Fee | None currently identified through substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[6 empty] | TR11 | Transport | Highways | Off-site Junction Improvements | A47 Normandy Way/A447 Ashby Road - Provision of a 100m widened southbound approach to include two approach lanes; Provision of a two-lane westbound exit from the junction; provision of a three lane northbound approach including a signal-controlled dedicated left turn lane; provision of a two lane exit to Normandy Way west and signal-controlled cycle and pedestrian crossing facilities | Proportionate financial contribution to LCC through s106 to design, consult on and implement a scheme of improvements that provides adequate mitigation of growth at Barwell and Earl Shilton | Barwell | Off-site | LCC | Developer | 2031-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Information not yet available | £2,897.53 per dwelling - total contribution towards: - A5 Longshoot / Dodwells - Desford Crossroads junction improvement - Public Right of Way Improvements as detailed within the submitted documents - Ashby Road / Normandy Way junction improvement - Travel Packs - Travel Plan Monitoring Fee | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Medium | Planning Application - Publicly available
[6 empty] | TR22 | Transport | Highways | Off-site Junction Improvements | Desford Lane Junction Improvement Scheme - Junction to be upgraded to a signalised junction | Contribution still to be agreed through S106 | Barwell | Off-site | LCC | Developer | 2031-2035 | Critical | Information not yet available | 12407711 | S106, Local Authority | S106 contributions from multiple sites | £2,897.53 per dwelling attributed to the residential aspect of the development, no funding attributed to the employment uses - Total contribution towards: - A5 Longshoot / Dodwells - Desford Crossroads junction improvement - Public Right of Way Improvements as detailed within the submitted documents - Ashby Road / Normandy Way junction improvement - Travel Packs - Travel Plan Monitoring Fee | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
[6 empty] | TR15 | Transport | Highways | Off-site Junction Improvements | A5/Dodwells Junction Improvement Scheme - Additional Lane on Dodwells Road | Contribution defined within agreed S106 | Barwell | Off-site | LCC | Developer | 2031-2035 | Critical | Information not yet available | 1901750 | S106 contributions from multiple sites | S106 contributions from multiple sites | £2,897.53 per dwelling attributed to the residential aspect of the development, no funding attributed to the employment uses - Total contribution towards: - A5 Longshoot / Dodwells - Desford Crossroads junction improvement - Public Right of Way Improvements as detailed within the submitted documents - Ashby Road / Normandy Way junction improvement - Travel Packs - Travel Plan Monitoring Fee | None currently identified. Substantive response provided by LCC Highways on 29 August 2025 with draft conditions. | Medium | Planning Application - Publicly available
[6 empty] | G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Barwell | Off-site | Cadent Gas | HBBC, Developer | 2026-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Information not yet available | Developer contribution will be ascertained at planning application stage. | None identified | Low | Cadent Gas analysis submitted to study (May 2026)
[6 empty] | G02 | Gas | Network upgrades | Offsite reinforcement - Medium Pressure Gas Network | Upgrades to medium pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | Barwell | Off-site | Cadent Gas | HBBC, Developer | 2026-2035 | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Information not yet available | Developer contribution will be ascertained at planning application stage. | None identified | Low | Cadent Gas analysis submitted to study (May 2026)
Leicestershire-wide infrastructure | [5 empty] | Refer to Leicestershire Wide Infrastructure on Housing Sheet
[6 empty] | TR46 | Transport | Rail | Midlands Rail Hub | Midlands Rail Hub - upgrades to the existing lines around Birmingham which will see an increase in capacity on services serving and passing through Hinckley | SOBC funded by DfT. No scheme funding for east section. | Regional | Off-site | Network Rail (To become Great British Rail from April 2027) | DFT | 2031-2045 | Desirable | Information not yet available | £1.75 billion | Central Government | No funding for proposals in East Midlands | No proposed date for funding to be allocated | Proposals for the East Midlands area are unfunded and have no certainty | High | Derived from discussions with Midlands Connect
[6 empty] | TR55 | Transport | Highways | Highway Improvements | A5 Dodwells to Longshoot Improvement Scheme | Extracted from the RIS3/RIS4 Pipeline | Hinckley | Off-site | National Highways | LCC | 2026-2045 | Desirable | Information not yet available | Cost subject to ongoing scoping and development | Central Government | Information not yet available | To be developed in RIS 3 (2026-2031) for construction in RIS4 (2031-2036) | Scheme still needs to be designed and costed and will need to be included in the Route Investment Strategy for Road Period 4. | High | Road Investment Strategy 3 (RIS3) 2026 to 2031 (March 2026)
[6 empty] | TR56 | Transport | Highways | Highway Improvements | A5 Concept Link Scheme | Scheme to connect the A47 and A5 to the west of Hinckley | Hinckley | Off-site | LCC | National Highways | 2026-2045 | Desirable | Information not yet available | Cost subject to ongoing scoping and development | Central Government, Local Authority | Information not yet available | Scheme presented to LCC Cabinet on 12 September 2025. Recommendation to consult with HBBC to support work on the Local Plan and to continue to develop the scheme. | Scheme will require viability assessment, detailed design, a business case to demonstrate value for money and investment from Central Government to be deliverable. | High | Wider discussions with stakeholders including HBBC, LCC and WCC. LCC Committee report accessed at https://democracy.leics.gov.uk/documents/s191532/Final%20A5%20Concept%20Cabinet%20Report%20120925.pdf

## Scheme Ref. List
Scheme Reference ID | Topic | Sub Topic | Project Name | Project Description | Project Notes | Sites | Settlement | On-site / Off-site | Delivery body | Other key stakeholder(s) or delivery bodies | Priority | Cost apportioned to site developer(s) | Estimated cost of total scheme | All funding sources for total scheme | Developer contribution towards expected funding gap | Cost Notes | Deliverability challenges | Overall implementation challenge | Source(s)
TR03 | Transport | Active Travel | Off-Site Footway Construction | Construction of a footway along Barton Road with associated crossing infrastructure | To be delivered prior to occupation as part of access proposals | AS455 | Barlestone | Off-site | Developer, Contractor | LCC | Critical | 70000 | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Low | Planning Application - Publicly available
TR04 | Transport | Bus | Enhancement of number 2 bus service | The enhanced 2 service will compliment the existing service between Barwell and Hinckley, and provide further connections to Hinckley rail station which will make use of the proposed improvements to the rail station and creation of a public transport interchange. | The enhancement of this service will align with the phasing of the development, with a 30 minute frequency service (one additional bus) being provided at occupation of 1,250 dwellings, and the 20 minute frequency service being provided at full occupation. | AS58 | Barwell | Off-site | Developer, Bus Operator | LCC | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
TR05 | Transport | Bus | Bus Stop Construction | Bus stops to be constructed along Stapleton Lane which is along the 159 Route. | Exact locations to be confirmed upon engagement with stakeholders | AS58 | Barwell | Off-site | LCC | Bus operator | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
TR06 | Transport | Bus | Bus Stop Construction | Bus stops to be constructed internally within the site within 400m walking distance of occupiers, with shelters, raised kerbing, bus service information | Subject to masterplan design principles | AS58 | Barwell | On-site | LCC | Bus operator, Developer | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
TR07 | Transport | Bus | Bus service information | A financial contribution can be made to the provision of public transport infrastructure and the implementation of Real Time Passenger Information (RTPI). | Funding will be provided for a set period following full occupation in order to assist the service in reaching commerciality. | AS58 | Barwell | Off-site | LCC | Developer | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
TR08 | Transport | Active Travel | Internal Walking and Cycling routes | Within the site, a series of shared footway / cycle tracks will be provided along with retention/diversion of existing walk routes, as indicated below. The principles of these include: - Partial diversion of the public footpath no. U36 forming part of the Leicestershire Round to within a landscaped area; - A new footpath/ cycle path along the western edge of the site connecting PROW T99 and T58; - Retention and/or minor diversions of the following PROWs, U33, U35, T58, T97 and T99; - A new footpath/ cycle path from PROW U36, the Leicestershire Round, to Hinckley Road to the south west of the site; and - Retention and partial diversion of existing public footpaths within the site, which link to Mill Street, Moat Way, and Hereford Close / Galloway Close | To be designated within site masterplan | AS58 | Barwell | On-site | Developer, Contractor |  | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
TR09 | Transport | Active Travel | Connection to Public right of way | There is also potential to upgrade the existing PROWs in Barwell to provide enhanced pedestrian and cycle connectivity for existing and future residents of Barwell and Barwell SUE. | No exact scheme proposed at this stage | AS58 | Barwell | Off-site | LCC | Developer | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | Planning Application - Publicly available
TR10 | Transport | Active Travel | Production of Framework Travel Plan | Applicant to appoint a travel plan coordinator to enforce the proposals within the Framework Travel Plan | The Framework Travel Plan would remain a ‘living document’, that will evolve and be updated by the Framework Travel Plan Coordinator to respond to local traffic conditions and opportunities for sustainable transport promotion, including schemes being implemented by the local highway authority and local transport stakeholders including bus operators. | AS58 | Barwell | Off-site | Developer | LCC | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | S106 contribution from AS58 Barwell SUE to be used towards: A5 Longshoot / Dodwells Desford Crossroads junction improvement Public Right of Way Improvements as detailed within the submitted documents Ashby Road / Normandy Way junction improvement Travel Packs Travel Plan Monitoring Fee | None currently identified. Substantive response provided by LCC Highways on 25 September 2025 with draft conditions. | Low | S106 agreement for 12/00295/OUT
TR11 | Transport | Highways | Off-site Junction Improvements | A47 Normandy Way/A447 Ashby Road - Provision of a 100m widened southbound approach to include two approach lanes; Provision of a two-lane westbound exit from the junction; provision of a three lane northbound approach including a signal-controlled dedicated left turn lane; provision of a two lane exit to Normandy Way west and signal-controlled cycle and pedestrian crossing facilities | Proportionate financial contribution to LCC through s106 to design, consult on and implement a scheme of improvements that provides adequate mitigation of growth at Barwell and Earl Shilton | AS58, AS1029, AS1031 A, AS1031 B, LPR199 | Multi-locational | Off-site | LCC | Developer | Critical | Refer to details for the specific site in Housing or Employment sheets | Cost subject to ongoing scoping and development | S106, Local Authority / Central Government Funding | Developer contibution pooled with contributions from multiple sites. Pooled contributiions may need to contribute to other potential funding sources to deliver scheme | See site for details | Refer to details for the specific site in Housing or Employment sheets | Medium | Planning Application - Publicly available
TR12 | Transport | Active Travel | Off-Site Footway Construction | New footway construction along Kirkby Road to connect to existing pedestrian infrastructure | Outline Design Stage | LPR185 | Barwell | Off-site | LCC | Developer | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | Substantive response provided by LCC Highways on 12 September 2025 requesting further details. | Low | Planning Application - Publicly available
TR13 | Transport | Bus | Enhancement of number 1 bus service | The enhanced 1 service will offer an increased frequency | This is a temporary measure until internal spine road completed upon which a new bus service will run through site | AS237 | Earl Shilton | Off-site | LCC | Developer, Bus operator | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | Overall scheme implementation cost not known | None currently identified. Substantive response provided by LCC Highways on 17 May 2024 with draft conditions. | Low | Planning Application - Publicly available
TR14 | Transport | Active Travel | Internal Walking and Cycling routes | An extensive network of shared use walking and cycling routes within the site which also connect to the existing external network, including Astley Road, Masefield Road, Mill Lane, Breach Lane and Avenue South; complemented by wayfinding | Tie into existing | AS237 | Earl Shilton | On-site | Developer |  | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 17 May 2024 with draft conditions. | Low | Planning Application - Publicly available
TR15 | Transport | Highways | Off-site Junction Improvements | A5/Dodwells Junction Improvement Scheme - Additional Lane on Dodwells Road | Contribution defined within agreed S106 | AS58, AS1029, AS1031 A, AS1031 B, LPR199; LPR22 | Multi-locational | Off-site | LCC | Developer | Critical | Information not yet available | 1901750 | S106, Local Authority, Central Government Funding | Developer contibution pooled with contributions from multiple sites. Pooled contributiions may need to contribute to other potential funding sources to deliver scheme | See site for details | Refer to details for the specific site in Housing or Employment sheets | Medium | JTE Study April 2026
TR16 | Transport | Active Travel | Off Site Pedestrian/cyclist improvement | Construction of a footway/cycleway on the A47 between the Leicester Road/Clickers Way roundabout and the junction of Desford Crossroads | n/a | AS237 | Earl Shilton | Off-site | LCC | Developer | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106, Local Authority Funding, Consolidated Active Travel Fund | Developer contribution towards other sources of funding for wider scheme | Scheme has not been submitted to planning yet | None currently identified. Substantive response provided by LCC Highways on 17 May 2024 with draft conditions. | Low | Planning Application - Publicly available
TR17 | Transport | Active Travel | Off-Site Footway Construction | New Footway Construction along Stoke Road to connect to existing Bus stop infrastructure and walking/cycling infrastructure. Also relevant Toucan crossing infrastructure along the A47 | Outline Design Stage | AS1029, AS1031 A, AS1031 B, LPR199 | Hinckley | Off-site | Developer | LCC | Critical | Information not yet available | Cost subject to ongoing scoping and development | S278 | Developer contribution towards other sources of funding for wider scheme | Funded through a mix of S106 contributions from other sites | Highways contribution agreed in conjunction with planning consent 24/00264/OUT. Total funding package for schem needs to be identified. | Medium | Planning Application - Publicly available
TR18 | Transport | Bus | Bus Service Provision | Extension of 153 bus service outside of the site. Should phase 2 come forwards, the service would be extended into the site | Cost around £170k for bus service outside of site. Consultation with LCC required for internal service | LPR139 | Market Bosworth | Off-site | LCC | Developer, Bus operator | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | N/A | Subject to ongoing discussions with the local bus operator (Arriva). | Low | Planning Application - Publicly available
TR19 | Transport | Highways | Off-Site Carriageway Improvements | Currently, there is an existing 7.5 tonne (except for loading) weight restriction in force on Station Road immediately to the east of the existing industrial estate access. The Applicant is proposing to relocate the weight restriction to the east of the Kyngs Golf Club access and west of the junction of Godsons Hill with Station Road. | TRO required with contributions through S106 | LPR139 | Market Bosworth | Off-site | LCC | Developer | Critical | 7500 | 7500 | S106 | Fully funded by developer | N/A | None currently identified | Unclear | Planning Application - Publicly available
TR20 | Transport | Active Travel | Off-Site Footway Improvements | Appropriate resurfacing of public footpath S26 and street lighting provision. As well as Improvements to surfacing, waymarking and lighting for public footpath R29 within the sit. Improvements to surfacing, waymarking and lighting for public footpath R4 within the site and minor diversion of route through the site | Contribution defined within agreed S106 | LPR190 | Newbold Verdon | Off-site | LCC | Developer | Critical | 64306 | 64306 | S106 | Fully funded by developer | N/A | None currently identified. To be delivered in accordance with planning consent 24/01158/OUT. | Low | Planning Application - Publicly available
TR21 | Transport | Highways | Off Site Carriageway Improvements | Extension of 30mph speed limit across site access on Brascote Lane | Traffic Regulation Order required with contributions through S106 | LPR207 | Newbold Verdon | Off-site | LCC | Developer | Critical | 7500 | 7500 | S106 | Fully funded by developer | TRO cost defined within LCC highways reponse | None currently identified. Substantive response provided by LCC Highways on 11 December 2025 with draft conditions. | Low | Planning Application - Publicly available
TR22 | Transport | Highways | Off-site Junction Improvements | Desford Lane Junction Improvement Scheme - Junction to be upgraded to a signalised junction | Contribution agreed through S106 | AS237, LPR107 | Multi-locational | Off-site | LCC | Developer | Critical | 3548891 | 12408711 | S106, Local Authority Funding | Developer contibution pooled with contributions from multiple sites. Pooled contributiions may need to contribute to other potential funding sources to deliver scheme | See site for details | None currently identified. Substantive response provided by LCC Highways on 19 December 2025 with draft conditions. | Low | Planning Application - Publicly available
TR23 | Transport | Highways | Off-site Junction Improvements | Groby Road/Sacheverell Way Junction Improvement Scheme - Junction to be upgraded to a signalised junction | Contribution still to be agreed through S106 | LPR146 A + LPR146 B, LPR107 | Multi-locational | Off-site | LCC | Developer | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106, Local Authority Funding | Developer contribution towards other sources of funding for wider scheme | See site for details | Medium | See site for details | Planning Application - Publicly available
TR24 | Transport | Bus | Bus Stop Infrastructure | Potential to contribute towards Arriva Service 28 | Will help to fill gaps in service locally | LPR107 | Ratby | Off-site | LCC | Developer, Bus operator | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | Subject to negotiation with operator | None currently identified. Substantive response provided by LCC Highways on 19 December 2025 with draft conditions. | Low | Planning Application - Publicly available
TR25 | Transport | Active Travel | Off-Site Walking Infrastructure | Scope to upgrade PRoW within the area | No exact scheme proposed at this stage | LPR107 | Ratby | Off-site | LCC | Developer | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | Subject to scope | None currently identified. Substantive response provided by LCC Highways on 19 December 2025 with draft conditions. | Low | Planning Application - Publicly available
TR26 | Transport | Highways | Off-site Junction Improvements | Bull in the Oak Junction Improvements - Upgrade to a signalised junction | Proposed as a result of pressure on junction and other local developments | LPR207 | Newbold Verdon | Off-site | LCC | Developer | Critical | 607296 | £1.5-£2million | S106, Local Authority Funding | Developer contribution towards other sources of funding for wider scheme | Cost defined in S106 Agreement | None currently identified. Substantive response provided by LCC Highways on 11 December 2025 with draft conditions. | Low | Planning Application - Publicly available
TR27 | Transport | Active Travel | Off-Site Walking Infrastructure | Public Footpath S19 improvements | Contribution required from developer | LPR207 | Newbold Verdon | Off-site | LCC | Developer | Critical | 89785 | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | Cost defined in S106 Agreement | None currently identified. Substantive response provided by LCC Highways on 11 December 2025 with draft conditions. | Low | Planning Application - Publicly available
TR28 | Transport | Active Travel | Off-Site Walking Infrastructure | Footpath Construction along Bosworth Lane | Required to access existing footway provision | LPR207 | Newbold Verdon | Off-site | Developer | LCC | Critical | Information not yet available | Cost subject to ongoing scoping and development | S278 | Fully funded by developer |  | None currently identified. Substantive response provided by LCC Highways on 11 December 2025 with draft conditions. | Low | Planning Application - Publicly available
TR29 | Transport | Bus | Bus Service/Infrastructure | Routing of 27 service to run closer to or within the site, requiring new bus stop infrastructure | No proposal at this stage | LPR146 A + LPR146 B | Groby | On-site and off-site | Developer | LCC | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | Requirement for site to access sufficient bus service | Substantive response provided by LCC Highways on 26 March 2026 requesting further details. | Low | Planning Application - Publicly available
TR30 | Transport | Active Travel | Off-Site Walking Infrastructure | Proposed pedestrian refuge on Sacherevell Way to aid crossing movements | Two proposed crossings - one on the desire line from Brookvale College and to the east of the site | LPR146 A + LPR146 B | Groby | Off-site | Developer | LCC | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | Requirement for site to be accessed safely | Substantive response provided by LCC Highways on 26 March 2026 requesting further details. | Low | Planning Application - Publicly available
TR32 | Transport | Active Travel | Off-Site Walking Infrastructure | Proposed pedestrian refuge on Launde Road close to the junction with Countryman Way | Enabling connection to bus facilities | LPR70 | Markfield | Off-site | Developer | LCC | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | N/A | None currently identified. Substantive response provided by LCC Highways on 13 February 2026 with draft conditions. | Low | Planning Application - Publicly available
TR33 | Transport | Active Travel | Off-Site Walking Infrastructure | Tactile Paving provided for existing uncontrolled crossing at the junction between Launde Road and Rathby Road | Improving site connectivity | LPR70 | Markfield | Off-site | Developer | LCC | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | N/A | None currently identified. Substantive response provided by LCC Highways on 13 February 2026 with draft conditions. | Low | Planning Application - Publicly available
TR34 | Transport | Highways | Off-site Junction Improvements | Proposed improvements to Field Head roundabout. | Site to contribute to A511 Growth Corridor scheme. | LPR70 | Markfield | Off-site | LCC | Developer | Critical | 659340 | Cost subject to ongoing scoping and development | S106, Local Authority / Central Government Funding | Developer contribution towards other sources of funding for wider scheme | £4884 Per dwelling | None currently identified. Substantive response provided by LCC Highways on 13 February 2026 with draft conditions. | Low | Planning Application - Publicly available
TR35 | Transport | Active Travel | Cycling Infrastructure | Cycling Route A | Contained within JTE evidence. Further details to be provided in LCWIP. | LPR138 | Hinckley | Off-site | LCC | Developer | Essential | 1813660 | 1915969 | S106, Local Authority Funding | Developer contibution pooled with site AS173 expected to provide sufficient funding for scheme | Cost through S106 still to be apportioned to site | LCWIP hasn't been published. Priority of route unknown. Pooled contributions were anticipated from sites which are no longer being taken forward. | High | JTE Study April 2026
TR36 | Transport | Active Travel | Cycling Infrastructure | Cycling Route C | Contained within JTE evidence. Further details to be provided in LCWIP. | LPR22 | Hinckley | Off-site | LCC | Developer | Critical | 925757 | 925757 | S106, Local Authority | Fully funded by developer | To be funded by LPR22 according to JTE Costing Mitigation Report | LCWIP hasn't been published. Priority of route unknown. | Low | JTE Study April 2026
TR37 | Transport | Active Travel | Cycling Infrastructure | Cycling Route D |  | LPR44 | Burbage | Off-site | LCC | Developer | Critical | 1688347 | 1688347 | S106 | Fully funded by site |  | No planning application so will need to be negotiated during planning process | Low | JTE Study April 2026
TR38 | Transport | Active Travel | Cycling Infrastructure | Cycling Route I | Contained within JTE evidence. Further details to be provided in LCWIP. | LPR200 + LPR216 | Earl Shilton | Off-site | LCC | Developer | Essential | 2742336 | 2742336 | S106, Local Authority Funding | Fully funded by developer | To be funded by LPR200 according to JTE Costing Mitigation Report | LCWIP hasn't been published. Priority of route unknown. | Low | JTE Study April 2026
TR39 | Transport | Active Travel | Cycling Infrastructure | Cycling Route L | Contained within JTE evidence. Further details to be provided in LCWIP. | AS1029, AS1031 A, AS1031 B, LPR199 | Hinckley | Off-site | LCC | Developer | Essential | 928512 | 928512 | S106, Local Authority Funding | Fully funded by developer | Funded through S106 | LCWIP hasn't been published. Priority of route unknown. | Low | JTE Study April 2026
TR40 | Transport | Active Travel | Cycling Infrastructure | Cycling Route M | Contained within JTE evidence. Further details to be provided in LCWIP. | AS1029, AS1031 A, AS1031 B, LPR199 | Hinckley | Off-site | LCC | Developer | Essential | 10053151 | 10863889 | S106, Local Authority Funding | Developer contribution towards other sources of funding for wider scheme | Funded through a mix of local authority and S106 contributions | LCWIP hasn't been published. Priority of route unknown. | Low | JTE Study April 2026
TR41 | Transport | Active Travel | Cycling Infrastructure | Cycling Route N | Contained within JTE evidence. Further details to be provided in LCWIP. | LPR235 | New Settlement | Off-site | LCC | Developer | Essential | 23553373.46 | 24187219 | S106, Local Authority Funding | Developer contibution pooled with contribution from sites LPR168 and LPR192 expected to provide sufficient funding for scheme | Cost through S106 still to be apportioned to site | LCWIP hasn't been published. Priority of route unknown. Pooled contributions were anticipated from sites which are no longer being taken forward. | High | JTE Study April 2026
TR42 | Transport | Active Travel | Cycling Infrastructure | Cycling Route AB | Contained within JTE evidence. Further details to be provided in LCWIP. | LPR107 | Ratby | Off-site | LCC | Developer | Essential | 11176620 | 12391471 | S106, Local Authority Funding | Developer contribution pooled with contribution from sites LPR196 and LPR134 expected to provide sufficient funding for scheme | Cost through S106 still to be apportioned to site | LCWIP hasn't been published. Priority of route unknown. Pooled contributions expected from sites which are no longer being taken forward. | Medium | JTE Study April 2026
TR43 | Transport | Bus | Highway/Bus Service Infrastructure | Regent Street/The Borough - Removal of on-street parking on The Borough to make room for an additional Northbound Approach | Expected to mitigate the impact of additional traffic generation in areas where there are existing issues with delay and capacity | LPR138 | Hinckley | Off-site | LCC | Developer | Critical | 92405 | 92405 | S106 | Fully funded by developer | Due to low proposed cost this can be funded through S106 contribution | None currently identified | Unclear | Planning Application - Publicly available, JTE Report April 2026
TR44 | Transport | Multi Modal | Mobility Hub | Proposed Hinckley Train Station Mobility Hub | Proposed to facilitate modal interchange as a result of development | Leicestershire-wide infrastructure | Hinckley | Off-site | LCC | Network Rail | Desirable | Information not yet available | 1124855 | Active Travel England, Developer contributions | None | Only initially costed at this point | No funding secured at the time of publication. Amount of funding required of considerable scale. | High | JTE Study April 2026
TR45 | Transport | Bus | Bus Service | Bus service and infrastructure contribution in line with Leicestershire Planning Obligations Policy Appendix A: Highways and Transportation. Bus Stops to be constructed to LCC Highway Standards, where upgrading/relocation of existing bus stops is required. | LCC highways to advise where this is required on a site by site basis. | Leicestershire-wide infrastructure | Multi-locational | Off-site | LCC | Developer, Contractor | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106, Local Authority Funding | Developer contribution towards other sources of funding for wider scheme |  | None currently identified | Low | LCC Highways Development Management (HDM) Policy 1.
TR46 | Transport | Rail | Midlands Rail Hub | Midlands Rail Hub - upgrades to the existing lines around Birmingham which will see an increase in capacity on services serving and passing through Hinckley | SOBC funded by DfT. No scheme funding for east section. | Leicestershire-wide infrastructure | Multi-locational | Off-site | Network Rail (To become Great British Rail from April 2027) | DFT | Regionally-critical infrastructure necessitated beyond Local Plan process | None | £1.75 billion | Central Government | Scheme reliant on significant capital funding from central government, beyond the scale of developer contributions | No proposed date for funding to be allocated | Proposals for the East Midlands area are unfunded and have no certainty | High | Derived from discussions with Midlands Connect
TR47 | Transport | Highways | Parking | Provide parking for all user types and electric vehicle charging provision in line with minimum standards specified by LCC Highways Design Guide. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | LPR152 + LPR227, LPR151 A, LPR200 + LPR216, LPR181, LPR31, LPR268, LPR235, LPR94 B, AS33; LPR241, LPR16A, LPR259, LPR44, LPR243, LPR22, LPR95 | Multi-locational | On-site | Developer, Contractor | LCC | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Design Guide.
TR48 | Transport | Active Travel | Walking/Cycling Infrastructure | Effective masterplanning to give priority to pedestrians / cyclists and maximise uptake of sustainable travel choices in accordance with LCC Highways Development Management (HDM) Policy 1. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | LPR152 + LPR227, LPR151 A, LPR200 + LPR216, LPR181, LPR31, LPR268, LPR235, LPR94 B, AS33; LPR241, LPR16A, LPR259, LPR44, LPR243, LPR22, LPR95 | Multi-locational | On-site | Developer, Contractor | LCC, National Highways, Warwickshire County Council | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 1.
TR49 | Transport | Highways | Highway access, safety and mitigation | Ensure that highway access can safely be provided and that operational traffic impacts can be acceptably mitigated in accordance with LCC Highways Development Management (HDM) Policy 2, 3 and 4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | LPR152 + LPR227, LPR151 A, LPR200 + LPR216, LPR181, LPR31, LPR268, LPR235, LPR94 B, AS33; LPR241, LPR16A, LPR259, LPR44, LPR243, LPR22, LPR95 | Multi-locational | Off-site | Developer | LCC, National Highways, Warwickshire County Council | Critical | Fully funded by developer (costs not yet developed) | Cost subject to ongoing scoping and development | S278 | Fully funded by developer |  | None currently identified | Unclear | LCC Highways Development Management (HDM) Policy 2, 3 and 4.
TR50 | Transport | Highways | Off Site Carriageway Improvements | A50 Field Head Roundabout Improvements | Site to contribute to A511 Growth Corridor scheme. | LPR94 A | Markfield | Off-site | LCC | Developer | Critical | 1377288 | Cost subject to ongoing scoping and development | S106, Local Authority Funding | Developer contribution towards other sources of funding for wider scheme | £4884 cost per dwelling factor applied | None currently identified. Highways contribution agreed in conjunction with planning consent 22/01153/DOV. | Low | Planning Application - Publicly available
TR51 | Transport | Highways | Bus infrastructure | Bus stops in vicinity of the site to be improved to include real time information and bus boarder kerbs. | Required due to increased public transport trips from the site | LPR94 A | Markfield | Off-site | LCC | Developer, Bus operator | Critical | Information not yet available | Cost subject to ongoing scoping and development | S106 | Fully funded by developer | N/A | None currently identified | Low | Planning Application - Publicly available
TR52 | Transport | Bus | Bus Service | Effective masterplanning to facilitate access to passenger transport in accordance with LCC Highways Development Management (HDM) Policy 1 and Passenger Transport Policy PTP4. | To be developed on a site by site basis at the planning application stage in consultation with LCC. | LPR152 + LPR227, LPR151 A, LPR200 + LPR216, LPR181, LPR31, LPR268, LPR235, LPR94 B, AS33; LPR241, LPR16A, LPR259, LPR44, LPR243, LPR22, LPR95 | Multi-locational | On-site and off-site | Developer, Contractor | Developer, Contractor | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | Fully funded by developer | None currently identified | Unclear | Application to be brought forward in line with planning policy.
TR53 | Transport | Multi Modal | Mobility Hub | Proposed East Shilton Mobility Hub | Proposed to facilitate modal interchange as a result of development | Leicestershire-wide infrastructure | Earl Shilton | Off-site | LCC | Network Rail | Desirable | Information not yet available | 571817 | Active Travel England, Developer contributions | None | Only initially costed at this point | No funding secured at the time of publication. Amount of funding required of considerable scale. | High | JTE Study April 2026
TR54 | Transport | Highways | Off Site Junction mitigation | Modelling of the additional allocations may result in additional mitigation being identified. To be confirmed upon completion of further JTE modelling to assess the impact of the additional Local Plan allocations on the highway network. | Current evidence base of the South Leicestershire JTE, does not reflect all of the allocations | Leicestershire-wide infrastructure | Multi-locational | Off-site | LCC | Contractor | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, central government | Developer contribution towards other sources of funding for wider scheme | N/A | Need to understand position from modelling in order to understand challenges in more detail | High | Information to be published in Summer 2026
TR55 | Transport | Highways | Highway Improvements | A5 Dodwells to Longshoot Improvement Scheme | Extracted from the RIS3/RIS4 Pipeline | Leicestershire-wide infrastructure | Hinckley | Off-site | National Highways | LCC | Desirable | Information not yet available | Cost subject to ongoing scoping and development | Central Government | Developer contribution towards other sources of funding for wider scheme | To be developed in RIS 3 (2026-2031) for construction in RIS4 (2031-2036) | Scheme still needs to be designed and costed and will need to be included in the Route Investment Strategy for Road Period 4. | High | Road Investment Strategy 3 (RIS3) 2026 to 2031 (March 2026)
TR56 | Transport | Highways | Highway Improvements | A5 Concept Link Scheme | Scheme to connect the A47 and A5 to the west of Hinckley | Leicestershire-wide infrastructure | Hinckley | Off-site | LCC | National Highways | Regionally-critical infrastructure necessitated beyond Local Plan process | Information not yet available | Cost subject to ongoing scoping and development | Central Government, Local Authority | Developer contribution towards other sources of funding for wider scheme | Scheme presented to LCC Cabinet on 12 September 2025. Recommendation to consult with HBBC to support work on the Local Plan and to continue to develop the scheme. | Scheme will require viability assessment, detailed design, a business case to demonstrate value for money and investment from Central Government to be deliverable. | High | https://democracy.leics.gov.uk/documents/s191532/Final%20A5%20Concept%20Cabinet%20Report%20120925.pdf
TR57 | Transport | Active Travel | Footway/cycleway Provision | • New footway links to connect the proposed development to existing facilities on London Road and Dr Wright Close • New foot/cycle link to Croftway • New footpaths within the site to link to existing footpaths and public rights of way • Uncontrolled pedestrian crossing facilities at the London Road/Croftway/Main Street junction | Required to mitigate proposed walking/cycling trips | LPR94 A | Markfield | On-site and off-site | Developer | LCC | Critical | Information not yet available | Cost subject to ongoing scoping and development | S278 | Fully funded by developer | Costs not yet develooped for the described scheme | None currently identified | Low | Planning Application - Publicly available
TR58 | Transport | Rail | Coventry - Leicester - Nottingham Rail Service | Reinstatement of direct rail services between Coventry, Leicester and Nottingham | Reduction in passenger journey times | Leicestershire-wide infrastructure | Regional | Off-site | Midlands Connect | LCC | Regionally-critical infrastructure necessitated beyond Local Plan process | Information not yet available | Cost subject to ongoing scoping and development | Central Government | Scheme reliant on significant capital funding from central government, beyond the scale of developer contributions | Midlands Connect submitted a Strategic Outline Business Case to the Department for Transport in Spring 2025 and should this be successful, the next stage will be the submission of an Outline Business Case. | Scheme requires more detailed work on the engineering aspects of the project, as well as further investigation into the benefits. | High | https://www.midlandsconnect.uk/media/saxnvkbw/midlands-connect-coventry-to-leicester-passengers-report.pdf
TR59 | Transport | Rail | Nuneaton Parkway | New P&R station at Nuneaton Parkway - location TBC | Midlands Connect have identified Nuneaton Parkway as a priority scheme in their recent Strategic Park and Ride study and concluded that the station (along with improved services) is likely to help intercept vehicle trips from the Strategic Road Network and thereby contribute to a reduction in car mileage/carbon and town/city centre congestion. | Leicestershire-wide infrastructure | Regional | Off-site | Midlands Connect | WCC | Regionally-critical infrastructure necessitated beyond Local Plan process | Information not yet available | Cost subject to ongoing scoping and development | Central Government | Scheme reliant on significant capital funding from central government, beyond the scale of developer contributions | The County Council will undertake a refresh of the high-level business case viability before carrying out a more significant piece of work to produce a Strategic Outline Business Case (SOBC) for the scheme. It is anticipated that this update along with the work to develop the SOBC will be undertaken in 2026/27. | Warwickshire County Council has undertaken a high-level feasibility study to ascertain if the station is likely to have a positive Business Case. A range of site options have been identified where the station could be located, this approach has included an assessment of the ‘long’ list of sites to determine a preferred location. | High | https://www.rugby.gov.uk/documents/20124/6836086/Nuneaton+Parkway+Safeguarding+document.pdf/bfd7301b-6569-43fa-e570-67eec48fc1ca?t=1767878673573
EL1 | Electric | Network upgrades | Off site reinforcement - Electricity | Upgrades to electricity network to service proposed development site | National Grid Electricity Distribution grid capacity assessment indicates that work will be required to service the proposed development site given current capacity constraints in the vicinity. | LPR185, AS237, LPR200 + 216, AS1029, AS1031 A, AS1031 B, LPR199, LPR31, LPR138, LPR268, LPR235 | Multi-locational | Off-site | National Grid Electricity Distribution |  | Critical | None | Cost subject to ongoing scoping and development | NGED | None | Developer not expected to pay for off-site reinforcement. Utility provider solely responsible for funding. | None currently identified | Unclear | Arup assessment against National Grid Electricity Distribution online Capacity Maps submitted for Phase 2 Addendum study - Autumn 2025
G01 | Gas | Network upgrades | Offsite reinforcement - Low Pressure Gas Network | Upgrades to low pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | LPR152 +LPR227, LPR221, AS455, AS237, LPR200 + LPR216, LPR146 A + LPR146 B, AS1029, AS1031 A, AS1031 B, LPR199, LPR31, LPR268, LPR235, LPR139, LPR94 A, LPR94 B, AS58; LPR241, LPR16A, LPR259, LPR22, LPR95 | Multi-locational | Off-site | Cadent Gas | HBBC, Developer | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Low | Caden Gas analysis submitted to study (March 2026)
G02 | Gas | Network upgrades | Off site reinforcement - Medium Pressure Gas | Upgrades to medium pressure gas network to service proposed development site. | Reinforcement works required to support corresponding gas network facilities given current capacity and expected growth in demand from expected population increase on site. Developer contribution to upgrade works will be required, but this will need to be discussed further with Cadent | LPR151 A, LPR235, AS58; LPR16A, LPR259, LPR243, AS237 | Multi-locational | Off-site | Cadent Gas | HBBC, Developer | Critical | Information not yet available | Cost subject to ongoing scoping and development | Developer contribution, Cadent Gas | Developer contribution towards utility provider funding |  | None currently identified | Unclear | Caden Gas analysis submitted to study (March 2026)
HE1 | Healthcare | Primary Healthcare | Healthcare facility capacity development | Enhancement and/or extension to existing infrastructure | Leicester, Leicestershire and Rutland ICB to work with local practice(s) to develop suitable plan to mitigate growth impact | LPR152 + LP227, LPR221, AS455, LPR185, LPR86, AS237, LPR200 + LPR216, LPR146 A + LPR146 B, LPR181, AS1029, AS1031 A, AS1031 B, LPR199, LPR31, LPR138, PR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR190, LPR107, AS33 | Multi-locational | Off-site | NHS ICB | HBBC | Critical | Refer to details for the specific site in Housing or Employment sheets | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contribution, NHS ICB | Developer contribution towards other sources of funding for wider scheme | Costs based on NHS ICB internal calculations based housing growth impact. Costs are based on 2026 costs dataset. | Refer to details for the specific site in Housing or Employment sheets | See site for details | Stakeholder engagement with Leicester, Leicestershire & Rutland NHS ICB
OS1 | Open Space | Provision of Open Space | On-Site Provision | Provision of open spaces on-site | On-site space provision and financial contribution towards those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | LPR152 + LPR227, LPR221, AS455, LPR185, LPR151 A, LPR86, LPR200 + LPR216, LPR181, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR207, AS33 | Multi-locational | On-site | Developer |  | Essential | Refer to details for the specific site in Housing or Employment sheets | Refer to details for the specific site in Housing or Employment sheets | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
OS2 | Open Space | Maintenance of Open Space | On-Site Maintenance | Maintenance of open spaces on-site | Financial contribution towards maintenance of open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. Contribution figures reflect a 20-year contribution period. | LPR152 + LPR227, LPR221, AS455, LPR185, LPR151 A, LPR86, LPR200 + LPR216, LPR181, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR207, AS33 | Multi-locational | On-site | HBBC / Local Parish |  | Essential | Refer to details for the specific site in Housing or Employment sheets | Cost subject to ongoing scoping and development | Developer contributions | Fully funded by developer | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
OS3 | Open Space | Provision of Open Space | Off-Site Provision | Provision of open spaces off-site, in the vicinity of the site | Off-site space provision and financial contribution to those spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens. | LPR152 + LPR227, LPR221, AS455, LPR185, LPR151 A, LPR86, LPR181, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR190, LPR207, AS33 | Multi-locational | Off-site | HBBC / Local Parish |  | Essential | Refer to details for the specific site in Housing or Employment sheets | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
OS4 | Open Space | Maintenance of Open Space | Off-Site Maintenance | Maintenance of open spaces off-site, in the vicinity of the site | Financial contribution towards maintenance of off-site open spaces based on a per dwelling and minimum site area contribution, determined by HBBC, across all sites, against the key typologies of allotments, amenity green space, equipped play, natural & semi-natural space and/or parks & gardens.. Contribution figures reflect a 10-year contribution period. | LPR152 + LPR227, LPR221, AS455, LPR185, LPR151 A, LPR86, LPR181, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR207, AS33 | Multi-locational | Off-site | HBBC / Local Parish |  | Essential | Refer to details for the specific site in Housing or Employment sheets | Broader, local infrastructure-sector maintenance scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, National Lottery, charitable foundations | Developer contribution towards other sources of funding for wider scheme | HBBC calculations based on figures provided by Hinckley and Bosworth Borough Council Open Space Assessment 2025 | None currently identified | Unclear | HBBC submission to the study (May 2026)
SC1 | Social Care and Care Services | Extra Care | Extra Care facilities | New and/or expanded extra care facilities in Leicestershire and bordering counties accessible for residents of Hinckley & Bosworth | New and/or extra care facilities are required to accommodate cumulative growth from all new sites | Leicestershire-wide infrastructure | Multi-locational | Off-site | Private developer | LCC, HBBC | Critical | Information not yet available | Cost subject to ongoing scoping and development | Private provider, LCC, HBBC | None | New and/or expanded Extra Care facilities are typically paid for by private providers, who are reliant on LCC and HBBC funds to support residents in these car facilities. Developers of new housing sites are not expected to contribute to this infrastructure. | LCC in their engagement for this study suggested there were no outstanding obstacles to the delivery of extra care facilities across Leicestershire of note and worth highlighting in this study | Low | Stakeholder engagement with LCC Strategic Services (Adults & Communities)
WA1 | Waste |  | Waste services contributions | Contribution towards waste facilities resulting from increased demand for services from site development (unspecified) |  | AS58, AS1029, AS1031 A, AS1031 B, LPR199, LPR190 | Multi-locational | Off-site | HBBC and LCC |  | Critical | Refer to details for the specific site in Housing or Employment sheets | Broader, local infrastructure-sector capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, local authority, central government, EPR scheme | Developer contribution towards other sources of funding for wider scheme | See site for details | None currently identified | Unclear | Planning Application - Publicly available
WW01 | Wastewater | Network upgrades | Off site capacity upgrades - Sewerage | Upgrades to sewage treatment work and/or receiving sewerage network to service proposed development site | STW’s desktop review identified that the site’s known network constraints are that the size of site will likely have an adverse impact on the downstream network and PS performance.and that it is assumed to be able to connect to the PS Desford - Bambrook Close northwest of the site. The northeast section of the site will require pumping due to topography, while the southwest section can be gravity connected. | LPR151 A, AS237, LPR200 + LPR216, AS1029, AS1031 A, AS1031 B, LPR199, LPR31, LPR235, LPR94 A | Multi-locational | Off-site | Severn Trent Water | HBBC | Critical | Refer to details for the specific site in Housing or Employment sheets | Cost subject to ongoing scoping and development | None | All network upgrade works required due to growth are funded through Severn Trent Water's Asset Management Programme (AMP) cycle. Developers are unlikely to be asked for a contribution. | See site for details | None currently identified | Unclear | Severn Trent Water assessment of sewerage provision for proposed development sites submitted as part of this study
P01 | Policing |  | Policing and Community Safety Contributions | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives. | Mitigation to meet policing demands generated by major population growth. | LPR152 + LPR227, LPR221, AS455, LPR151 A, LPR185, LPR86, LPR200 + LPR216, LPR146 A + LPR146 B, LPR181, LPR31, LPR138, LPR268, LPR235, LPR139, LPR190, LPR70, LPR94 A, LPR94 B, LPR190, LPR207, LPR107, AS33 | Multi-locational | On-site and off-site | Leicestershire Police | HBBC | Desirable | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
P02 | Policing |  | Policing and Community Safety Contributions | Fluid infrastructure approach to policing and community safety capacity needs proposed by Leicestershire Police with additional identified requirement for additional on-site mitigation (for example, early phase PCSOs and more intensive community safety measures). | Contributions covering essential personal equipment (NPA), central support, infrastructure and estates, fleet vehicles, policing technology improvements and crime reduction initiatives as well as Community Support Officers. | AS58, AS237, LPR200 + LPR216, LPR235, AS1029, AS1031 A, AS1031 B and LPR199 | Multi-locational | On-site and off-site | Leicestershire Police | HBBC | Desirable | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, central government, local taxation | Developer contribution towards other sources of funding | Estimated cost produced using the policing methodology formula, which models predicted crime levels and population growth, to quantify the additional demand on policing arising from new development. | Leicestershire Police, as confirmed in their latest Estates Strategy, do not foresee significant barriers to delivery for infrastructure capacity development. Where physical expansion of a particular building is constrained, mitigation can be delivered through alternative and complementary solutions, including internal reconfiguration, use of satellite or shared facilities, and investment in fleet, digital capability, and centralised infrastructure (such as custody or contact management facilities) serving the borough as a whole. There are no known constraints relating to staffing, technology, or operational capability that would prevent delivery of these solutions, subject to funding being secured. | Low | Written submissions from Leicestershire Police to this study
E01 | Education | Early Years | Early Years Contributions | Contributions to Early Years capacity expansion | This scheme details the required funding for necessary early years capacity expansion as a result of this site coming forward. | LPR152 + LPR227, LPR221, AS455, LPR151 A, LPR200 + LPR216, LPR146 A + LPR146 B, AS1029, AS1031 A, AS1031 B and LPR199, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR190, LPR207, LPR107 | Multi-locational | On-site and off-site | LCC |  | Critical | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | Refer to details for the specific site in Housing or Employment sheets | See site for details | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
E02 | Education | Primary School | Primary School Contributions | Contributions to Primary School capacity expansion | This scheme details the required funding for necessary primary school capacity expansion as a result of this site coming forward. | LPR152 + LPR227, LPR221, AS455, LPR151 A, LPR86, LPR200 + LPR216, LPR146 A + LPR146 B, LPR181, AS1029, AS1031 A, AS1031 B and LPR199, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR190, LPR207, LPR107, AS33 | Multi-locational | On-site and off-site | LCC |  | Critical | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. Due to contributions being calculated using expansion costs rather than new build costs, the overall cost may be higher than stated as LCC have indicated a new school may be required to accomodate growth from this site. | Refer to details for the specific site in Housing or Employment sheets | See site for details | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
E03 | Education | Secondary School | Secondary School Contributions | Contributions to Secondary School capacity expansion | This scheme details the required funding for necessary secondary school capacity expansion as a result of this site coming forward. | LPR152 + LPR227, LPR221, AS455, LPR151 A, LPR86, LPR200 + LPR216, LPR146 A + LPR146 B, LPR181, AS1029, AS1031 A, AS1031 B and LPR199, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR190, LPR207, LPR107, AS33 | Multi-locational | On-site and off-site | LCC |  | Critical | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | Refer to details for the specific site in Housing or Employment sheets | See site for details | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
E04 | Education | Post 16 | Post 16 Contributions | Contributions to Post 16 capacity expansion | This scheme details the required funding for necessary post-16 capacity expansion as a result of this site coming forward. | LPR152 + LPR227, LPR221, AS455, LPR151 A, LPR86, LPR200 + LPR216, LPR146 A + LPR146 B, LPR181, AS1029, AS1031 A, AS1031 B and LPR199, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR190, LPR207, LPR107, AS33 | Multi-locational | On-site and off-site | LCC |  | Critical | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | Refer to details for the specific site in Housing or Employment sheets | See site for details | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
E05 | Education | Primary SEND | Primary SEND Contributions | Contributions to Primary SEND capacity expansion | This scheme details the required funding for necessary primary school SEND capacity expansion as a result of this site coming forward. | LPR152 + LPR227, AS455, LPR151 A, LPR200 + LPR216, LPR146 A + LPR146 B, AS1029, AS1031 A, AS1031 B and LPR199, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR190, LPR207, LPR107 | Multi-locational | On-site and off-site | LCC |  | Critical | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | Refer to details for the specific site in Housing or Employment sheets | See site for details | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
E06 | Education | Secondary SEND | Secondary SEND Contributions | Contributions to Secondary SEND capacity expansion | This scheme details the required funding for necessary secondary school SEND capacity expansion as a result of this site coming forward. | LPR152 + LPR227, AS455, LPR151 A, LPR200 + LPR216, LPR146 A + LPR146 B, AS1029, AS1031 A, AS1031 B and LPR199, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR190, LPR207, LPR107 | Multi-locational | On-site and off-site | LCC |  | Critical | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | S106/CIL and DfE Capital and Growth funding | Fully funded by developer | Cost apportioned to site developer calculated using pupil yield data from LCC 2026-2031 School Places Strategy (yield for early years only taken from LCC 2019 Planning Obligations report) and expansion costs per place data provided by LCC for this study. Calculations follow DfE guidance to forecast maximum developer contribution, on expected yield rather than on local school capacity, with contributions redistributed to other identified school capacity projects if not required in vicinity. This allows for greater certainty that contribution is commensurate with the impact of the relevant development. This may be amended in later years based on unit type delivered and expected affect on yield. | Refer to details for the specific site in Housing or Employment sheets | See site for details | Contextual information provided by LCC for this study. Calculations utilise LCC 2026-2031 School Places Strategy, LCC 2019 Planning Obligations and LCC's submitted cost per place data for this study for inputs
S01 | Sports | Facilities | Swimming Pool | Provision of swimming pools based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | AS455, LPR185, LPR151 A, LPR86, LPR200 + LPR216, LPR146 A + LPR146 B, LPR181, AS1029, AS1031 A, AS1031 B and LPR199, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR190, LPR207, LPR107, AS33 | Multi-locational | On-site and off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | Essential | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
S02 | Sports | Facilities | Sports Hall | Provision of sports halls based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | AS455, LPR185, LPR151 A, LPR86, LPR200 + LPR216, LPR146 A + LPR146 B, LPR181, AS1029, AS1031 A, AS1031 B and LPR199, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR190, LPR207, LPR107, AS33 | Multi-locational | On-site and off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | Essential | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, National Governing Bodies for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
S03 | Sports | Facilities | Artificial Grass Pitch | Provision of artificial grass pitches (AGPs) based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | AS455, LPR185, LPR151 A, LPR86, LPR200 + LPR216, LPR146 A + LPR146 B, LPR181, AS1029, AS1031 A, AS1031 B and LPR199, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR190, LPR207, LPR107, AS33 | Multi-locational | On-site and off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | Essential | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions,Football Foundation and other National Governing Body for relevant sports. Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
S04 | Sports | Facilities | Tennis Courts | Provision of tennis courts based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | AS455, LPR185, LPR151 A, LPR86, LPR200 + LPR216, LPR146 A + LPR146 B, LPR181, AS1029, AS1031 A, AS1031 B and LPR199, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR190, LPR207, LPR107, AS33 | Multi-locational | On-site and off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | Essential | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Lawn Tennis Associations, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
S05 | Sports | Facilities | Bowls | Provision of bowls greens based on demand generated by site | In line with Sports England requirements, provision of capital facilities based on additional demand generated calculated as visits per week in the peak period. | AS455, LPR185, LPR151 A, LPR86, LPR200 + LPR216, LPR146 A + LPR146 B, LPR181, AS1029, AS1031 A, AS1031 B and LPR199, LPR31, LPR138, LPR268, LPR235, LPR139, LPR70, LPR94 A, LPR94 B, LPR190, LPR207, LPR107, AS33 | Multi-locational | On-site and off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | Essential | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Bowls England, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's SFC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
S06 | Sports | Pitches | Pitches | Pitch provision (natural grass pitches only) - capital cost | In line with Sports England requirements, provision of pitches (total pitch capital cost) | LPR151 A, LPR200 + LPR216, AS1029, AS1031 A, AS1031 B and LPR199, LPR131, LPR235 | Multi-locational | On-site and off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | Essential | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
S07 | Sports | Pitches | Pitch maintenance | Lifecycle cost for pitch maintenance per annum (applied across 10-year period) (natural grass pitches only) | In line with Sports England requirements, provision of costs for maintenance lifecycle (cost per annum of pitches) | LPR151 A, LPR200 + LPR216, AS1029, AS1031 A, AS1031 B and LPR199, LPR131, LPR235 | Multi-locational | On-site and off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | Essential | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Grass Pitch Maintenance Fund, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators
S08 | Sports | Pitches | Changing rooms | Provision of changing rooms for provided pitches (natural grass pitches only) | In line with Sports England requirements, provision of cost for changing rooms (total capital cost) | LPR151 A, LPR200 + LPR216, AS1029, AS1031 A, AS1031 B and LPR199, LPR131, LPR235 | Multi-locational | On-site and off-site | HBBC | Sport England, National Governing Body (relevant sport), LCC, Developer | Essential | Refer to details for the specific site in Housing or Employment sheets | Broader infrastructure capacity scheme across multiple assets and delivery years - not possible to define within the schedule | Developer contributions, Football Foundation and other National Governing Body for relevant sports, Sport England, HBBC | Developer contribution towards other sources of funding for wider scheme | Calculations provided by HBBC, utilising Sport England's PPC calculator | None currently identified | Unclear | HBBC calculations utilising standards from latest Playing Pitch Strategy and Sport England calculators

## Validation (hidden)
On-site / Off-site
On-site
Off-site
On-site and off-site